## Sheet1
UserCode | taskName | HoursWorked | OvertimeWorked | dateOfWork | ProjectJobId | ShiftType | ForemanName | IsVerified | JobName | estimatedHours | TaskId
BENDAN | Penthouse siding and coping | 8 |  | 2024-08-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-1 | Uploaded
JOHSCO | Roof screen wall | 8 |  | 2024-08-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.7 | 6446.0-2 | Uploaded
BENDAN | Commute to Site | 6 |  | 2024-07-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-3 | Uploaded
JOHSCO | Garage Gutters | 6 |  | 2024-07-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-4 | Uploaded
BENDAN | Paperwork | 3 |  | 2024-07-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-5 | Uploaded
CHAJAV | L10 deck panels | 3 |  | 2024-07-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-6 | Uploaded
CUSCAR | Column wraps @ podium | 3 |  | 2024-07-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-7 | Uploaded
GRETAR | Sheet metal roof @ L14 canopy | 3 |  | 2024-07-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-8 | Uploaded
JOHSCO | Wall panels @ entry vestibule | 3 |  | 2024-07-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-9 | Uploaded
BENDAN | Penthouse gutters and DS | 8 |  | 2024-07-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-10 | Uploaded
CHAJAV | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-07-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-11 | Uploaded
CUSCAR | Exterior window installation | 8 |  | 2024-07-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-12 | Uploaded
GRETAR | Facade metal panel installation | 8 |  | 2024-07-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-13 | Uploaded
JOHSCO | Basement waterproofing | 4 |  | 2024-07-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-14 | Uploaded
CARBRA | Elevator shaft framing | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-15 | Uploaded
NGUKHA | Site drainage installation | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-16 | Uploaded
BENDAN | Concrete foundation pouring | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-17 | Uploaded
CHAJAV | HVAC ductwork installation | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-18 | Uploaded
CUSCAR | Interior wall framing | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-19 | Uploaded
SLOKYL | Electrical conduit installation | 2 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-20 | Uploaded
CAMPHI | Fire sprinkler system installation | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.2 | 6446.0-21 | Uploaded
GRETAR | Roof membrane installation | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-22 | Uploaded
JOHSCO | Floor tile installation | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-23 | Uploaded
CARBRA | Drywall installation | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-24 | Uploaded
NGUKHA | Parking lot asphalt paving | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-25 | Uploaded
BENDAN | Landscape irrigation installation | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-26 | Uploaded
CHAJAV | Structural steel erection | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-27 | Uploaded
CUSCAR | Guardrail installation | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-28 | Uploaded
CAMPHI | Exterior painting | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.6 | 6446.0-29 | Uploaded
GRETAR | Interior door installation | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-30 | Uploaded
JOHSCO | Window caulking and sealing | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-31 | Uploaded
GOETRO | Ceiling grid installation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.6 | 6446.0-32 | Uploaded
COUMAR | Building insulation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.2 | 6446.0-33 | Uploaded
CARBRA | Hardwood flooring installation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-34 | Uploaded
NGUKHA | Crown molding installation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-35 | Uploaded
BENDAN | Kitchen cabinetry installation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-36 | Uploaded
CHAJAV | Bathroom fixture installation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-37 | Uploaded
CUSCAR | Tool organization | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-38 | Uploaded
CAMPHI | Team safety meeting | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-39 | Uploaded
STEJAC | Material delivery coordination | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-40 | Uploaded
GRETAR | Quality control inspection | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-41 | Uploaded
JOHSCO | Stair railing installation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-42 | Uploaded
GOETRO | Building permit processing | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-43 | Uploaded
COUMAR | Demolition work | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-44 | Uploaded
CARBRA | Scaffolding assembly | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-45 | Uploaded
NGUKHA | Masonry wall construction | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.9 | 6446.0-46 | Uploaded
BENDAN | Plumbing rough-in | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.9 | 6446.0-47 | Uploaded
CHAJAV | Exterior lighting installation | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-48 | Uploaded
CUSCAR | Rooftop HVAC unit installation | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-49 | Uploaded
CAMPHI | Subcontractor coordination | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-50 | Uploaded
WISJER | Curtain wall installation | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-51 | Uploaded
STEJAC | Balcony waterproofing | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-52 | Uploaded
GRETAR | Emergency exit signage installation | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-53 | Uploaded
JOHSCO | Project planning and scheduling | 4 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-54 | Uploaded
TRACCO | Security system wiring | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-55 | Uploaded
GOETRO | Penthouse siding and coping | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.8 | 6446.0-56 | Uploaded
COUMAR | Roof screen wall | 6 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-57 | Uploaded
CARBRA | Commute to Site | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-58 | Uploaded
NGUKHA | Garage Gutters | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-59 | Uploaded
BENDAN | Paperwork | 7 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-60 | Uploaded
BENDAN | L10 deck panels | 1 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-61 | Uploaded
CHAJAV | Column wraps @ podium | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-62 | Uploaded
HANTYL | Sheet metal roof @ L14 canopy | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-63 | Uploaded
CUSCAR | Wall panels @ entry vestibule | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-64 | Uploaded
SLOKYL | Penthouse gutters and DS | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-65 | Uploaded
CAMPHI | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-66 | Uploaded
WISJER | Exterior window installation | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-67 | Uploaded
STEJAC | Facade metal panel installation | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-68 | Uploaded
GRETAR | Basement waterproofing | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-69 | Uploaded
JOHSCO | Elevator shaft framing | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 9 | 6446.0-70 | Uploaded
GOETRO | Site drainage installation | 2 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-71 | Uploaded
GOETRO | Concrete foundation pouring | 6 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-72 | Uploaded
COUMAR | HVAC ductwork installation | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-73 | Uploaded
CARBRA | Interior wall framing | 7 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.1 | 6446.0-74 | Uploaded
NGUKHA | Electrical conduit installation | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-75 | Uploaded
BENDAN | Fire sprinkler system installation | 5 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-76 | Uploaded
CHAJAV | Roof membrane installation | 1.5 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-77 | Uploaded
CHAJAV | Floor tile installation | 6.5 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-78 | Uploaded
HANTYL | Drywall installation | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-79 | Uploaded
CUSCAR | Parking lot asphalt paving | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1 | 6446.0-80 | Uploaded
SLOKYL | Landscape irrigation installation | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-81 | Uploaded
CAMPHI | Structural steel erection | 2 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.1 | 6446.0-82 | Uploaded
CAMPHI | Guardrail installation | 6 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-83 | Uploaded
WISJER | Exterior painting | 3 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-84 | Uploaded
WISJER | Interior door installation | 5 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-85 | Uploaded
GRETAR | Window caulking and sealing | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-86 | Uploaded
JOHSCO | Ceiling grid installation | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-87 | Uploaded
GOETRO | Building insulation | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-88 | Uploaded
COUMAR | Hardwood flooring installation | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-89 | Uploaded
CARBRA | Crown molding installation | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-90 | Uploaded
NGUKHA | Kitchen cabinetry installation | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-91 | Uploaded
BENDAN | Bathroom fixture installation | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-92 | Uploaded
CHAJAV | Tool organization | 2 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-93 | Uploaded
CHAJAV | Team safety meeting | 6 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.4 | 6446.0-94 | Uploaded
HANTYL | Material delivery coordination | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-95 | Uploaded
CUSCAR | Quality control inspection | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-96 | Uploaded
SLOKYL | Stair railing installation | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-97 | Uploaded
CAMPHI | Building permit processing | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-98 | Uploaded
WISJER | Demolition work | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-99 | Uploaded
GRETAR | Scaffolding assembly | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-100 | Uploaded
JOHSCO | Masonry wall construction | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-101 | Uploaded
GOETRO | Plumbing rough-in | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-102 | Uploaded
COUMAR | Exterior lighting installation | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-103 | Uploaded
CARBRA | Rooftop HVAC unit installation | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-104 | Uploaded
NGUKHA | Subcontractor coordination | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-105 | Uploaded
BENDAN | Curtain wall installation | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-106 | Uploaded
CHAJAV | Balcony waterproofing | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-107 | Uploaded
HANTYL | Emergency exit signage installation | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-108 | Uploaded
SLOKYL | Project planning and scheduling | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-109 | Uploaded
CAMPHI | Security system wiring | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-110 | Uploaded
WISJER | Penthouse siding and coping | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-111 | Uploaded
STEJAC | Roof screen wall | 5 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-112 | Uploaded
GRETAR | Commute to Site | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-113 | Uploaded
JOHSCO | Garage Gutters | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-114 | Uploaded
GOETRO | Paperwork | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 9 | 6446.0-115 | Uploaded
COUMAR | L10 deck panels | 6 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-116 | Uploaded
CARBRA | Column wraps @ podium | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-117 | Uploaded
NGUKHA | Sheet metal roof @ L14 canopy | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-118 | Uploaded
BENDAN | Wall panels @ entry vestibule | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-119 | Uploaded
CHAJAV | Penthouse gutters and DS | 2 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-120 | Uploaded
CHAJAV | Sheet metal roof @ L14 canopy (roof build up) | 6 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-121 | Uploaded
HANTYL | Exterior window installation | 7.5 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-122 | Uploaded
SLOKYL | Facade metal panel installation | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-123 | Uploaded
CAMPHI | Basement waterproofing | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6 | 6446.0-124 | Uploaded
WISJER | Elevator shaft framing | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-125 | Uploaded
STEJAC | Site drainage installation | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-126 | Uploaded
GRETAR | Concrete foundation pouring | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.2 | 6446.0-127 | Uploaded
JOHSCO | HVAC ductwork installation | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-128 | Uploaded
GOETRO | Interior wall framing | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-129 | Uploaded
COUMAR | Electrical conduit installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.8 | 6446.0-130 | Uploaded
NGUKHA | Fire sprinkler system installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-131 | Uploaded
BENDAN | Roof membrane installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-132 | Uploaded
CHAJAV | Floor tile installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-133 | Uploaded
HANTYL | Drywall installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-134 | Uploaded
CUSCAR | Parking lot asphalt paving | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-135 | Uploaded
SLOKYL | Landscape irrigation installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-136 | Uploaded
CAMPHI | Structural steel erection | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-137 | Uploaded
WISJER | Guardrail installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-138 | Uploaded
STEJAC | Exterior painting | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-139 | Uploaded
GRETAR | Interior door installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-140 | Uploaded
JOHSCO | Window caulking and sealing | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-141 | Uploaded
GOETRO | Ceiling grid installation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-142 | Uploaded
COUMAR | Building insulation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-143 | Uploaded
CARBRA | Hardwood flooring installation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-144 | Uploaded
NGUKHA | Crown molding installation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-145 | Uploaded
CUTHAR | Kitchen cabinetry installation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-146 | Uploaded
BENDAN | Bathroom fixture installation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-147 | Uploaded
CHAJAV | Tool organization | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-148 | Uploaded
HANTYL | Team safety meeting | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-149 | Uploaded
CUSCAR | Material delivery coordination | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-150 | Uploaded
SLOKYL | Quality control inspection | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-151 | Uploaded
CAMPHI | Stair railing installation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-152 | Uploaded
WISJER | Building permit processing | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-153 | Uploaded
STEJAC | Demolition work | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-154 | Uploaded
GRETAR | Scaffolding assembly | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-155 | Uploaded
JOHSCO | Masonry wall construction | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-156 | Uploaded
GOETRO | Plumbing rough-in | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-157 | Uploaded
COUMAR | Exterior lighting installation | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-158 | Uploaded
CARBRA | Rooftop HVAC unit installation | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-159 | Uploaded
NGUKHA | Subcontractor coordination | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-160 | Uploaded
CUTHAR | Curtain wall installation | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-161 | Uploaded
BENDAN | Balcony waterproofing | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-162 | Uploaded
CHAJAV | Emergency exit signage installation | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-163 | Uploaded
HANTYL | Project planning and scheduling | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-164 | Uploaded
CUSCAR | Security system wiring | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-165 | Uploaded
SLOKYL | Penthouse siding and coping | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.8 | 6446.0-166 | Uploaded
CAMPHI | Roof screen wall | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-167 | Uploaded
WISJER | Commute to Site | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-168 | Uploaded
STEJAC | Garage Gutters | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-169 | Uploaded
GRETAR | Paperwork | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-170 | Uploaded
JOHSCO | L10 deck panels | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-171 | Uploaded
GOETRO | Column wraps @ podium | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-172 | Uploaded
COUMAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-173 | Uploaded
CARBRA | Wall panels @ entry vestibule | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-174 | Uploaded
NGUKHA | Penthouse gutters and DS | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-175 | Uploaded
CUTHAR | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-176 | Uploaded
BENDAN | Exterior window installation | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-177 | Uploaded
CHAJAV | Facade metal panel installation | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-178 | Uploaded
HANTYL | Basement waterproofing | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-179 | Uploaded
CUSCAR | Elevator shaft framing | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-180 | Uploaded
SLOKYL | Site drainage installation | 7.5 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-181 | Uploaded
CAMPHI | Concrete foundation pouring | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 9 | 6446.0-182 | Uploaded
WISJER | HVAC ductwork installation | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-183 | Uploaded
STEJAC | Interior wall framing | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.8 | 6446.0-184 | Uploaded
GRETAR | Electrical conduit installation | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-185 | Uploaded
JOHSCO | Fire sprinkler system installation | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-186 | Uploaded
GOETRO | Roof membrane installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-187 | Uploaded
COUMAR | Floor tile installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-188 | Uploaded
CARBRA | Drywall installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-189 | Uploaded
NGUKHA | Parking lot asphalt paving | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-190 | Uploaded
BENDAN | Landscape irrigation installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-191 | Uploaded
CHAJAV | Structural steel erection | 2 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-192 | Uploaded
CHAJAV | Guardrail installation | 6 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-193 | Uploaded
HANTYL | Exterior painting | 7.5 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-194 | Uploaded
CUSCAR | Interior door installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-195 | Uploaded
SLOKYL | Window caulking and sealing | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1 | 6446.0-196 | Uploaded
CAMPHI | Ceiling grid installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-197 | Uploaded
WISJER | Building insulation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-198 | Uploaded
STEJAC | Hardwood flooring installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-199 | Uploaded
GRETAR | Crown molding installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-200 | Uploaded
JOHSCO | Kitchen cabinetry installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-201 | Uploaded
GOETRO | Bathroom fixture installation | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-202 | Uploaded
COUMAR | Tool organization | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-203 | Uploaded
NGUKHA | Team safety meeting | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-204 | Uploaded
CUTHAR | Material delivery coordination | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-205 | Uploaded
BENDAN | Quality control inspection | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-206 | Uploaded
CHAJAV | Stair railing installation | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-207 | Uploaded
HANTYL | Building permit processing | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-208 | Uploaded
CUSCAR | Demolition work | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-209 | Uploaded
SLOKYL | Scaffolding assembly | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-210 | Uploaded
CAMPHI | Masonry wall construction | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-211 | Uploaded
WISJER | Plumbing rough-in | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4 | 6446.0-212 | Uploaded
STEJAC | Exterior lighting installation | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-213 | Uploaded
GRETAR | Rooftop HVAC unit installation | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-214 | Uploaded
JOHSCO | Subcontractor coordination | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.9 | 6446.0-215 | Uploaded
CARBRA | Curtain wall installation | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-216 | Uploaded
NGUKHA | Balcony waterproofing | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-217 | Uploaded
OSBKEV | Emergency exit signage installation | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-218 | Uploaded
CUTHAR | Project planning and scheduling | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-219 | Uploaded
BENDAN | Security system wiring | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-220 | Uploaded
CHAJAV | Penthouse siding and coping | 6 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-221 | Uploaded
HANTYL | Roof screen wall | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-222 | Uploaded
CUSCAR | Commute to Site | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-223 | Uploaded
SLOKYL | Garage Gutters | 5 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-224 | Uploaded
CAMPHI | Paperwork | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-225 | Uploaded
WISJER | L10 deck panels | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-226 | Uploaded
STEJAC | Column wraps @ podium | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-227 | Uploaded
GRETAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-228 | Uploaded
JOHSCO | Wall panels @ entry vestibule | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-229 | Uploaded
CARBRA | Penthouse gutters and DS | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-230 | Uploaded
NGUKHA | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-231 | Uploaded
OSBKEV | Exterior window installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-232 | Uploaded
CUTHAR | Facade metal panel installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-233 | Uploaded
BENDAN | Basement waterproofing | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-234 | Uploaded
CHAJAV | Elevator shaft framing | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-235 | Uploaded
HANTYL | Site drainage installation | 7.5 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.8 | 6446.0-236 | Uploaded
CUSCAR | Concrete foundation pouring | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-237 | Uploaded
SLOKYL | HVAC ductwork installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-238 | Uploaded
CAMPHI | Interior wall framing | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-239 | Uploaded
WISJER | Electrical conduit installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-240 | Uploaded
STEJAC | Fire sprinkler system installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-241 | Uploaded
GRETAR | Roof membrane installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-242 | Uploaded
JOHSCO | Floor tile installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-243 | Uploaded
NGUKHA | Drywall installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-244 | Uploaded
OSBKEV | Parking lot asphalt paving | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-245 | Uploaded
CUTHAR | Landscape irrigation installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-246 | Uploaded
BENDAN | Structural steel erection | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.3 | 6446.0-247 | Uploaded
CHAJAV | Guardrail installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.3 | 6446.0-248 | Uploaded
HANTYL | Exterior painting | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.8 | 6446.0-249 | Uploaded
CUSCAR | Interior door installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-250 | Uploaded
SLOKYL | Window caulking and sealing | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-251 | Uploaded
CAMPHI | Ceiling grid installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-252 | Uploaded
WISJER | Building insulation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-253 | Uploaded
STEJAC | Hardwood flooring installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-254 | Uploaded
GRETAR | Crown molding installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-255 | Uploaded
JOHSCO | Kitchen cabinetry installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-256 | Uploaded
BENDAN | Bathroom fixture installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-257 | Uploaded
BENDAN | Tool organization | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-258 | Uploaded
BENDAN | Team safety meeting | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-259 | Uploaded
BENDAN | Material delivery coordination | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-260 | Uploaded
BENDAN | Quality control inspection | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-261 | Uploaded
CAMPHI | Stair railing installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-262 | Uploaded
CAMPHI | Building permit processing | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-263 | Uploaded
CAMPHI | Demolition work | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-264 | Uploaded
CAMPHI | Scaffolding assembly | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-265 | Uploaded
CHAJAV | Masonry wall construction | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-266 | Uploaded
CHAJAV | Plumbing rough-in | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-267 | Uploaded
CHAJAV | Exterior lighting installation | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-268 | Uploaded
CHAJAV | Rooftop HVAC unit installation | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-269 | Uploaded
CHAJAV | Subcontractor coordination | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6 | 6446.0-270 | Uploaded
CUSCAR | Curtain wall installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-271 | Uploaded
CUSCAR | Balcony waterproofing | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-272 | Uploaded
CUSCAR | Emergency exit signage installation | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-273 | Uploaded
CUSCAR | Project planning and scheduling | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-274 | Uploaded
CUSCAR | Security system wiring | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.6 | 6446.0-275 | Uploaded
CUTHAR | Penthouse siding and coping | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-276 | Uploaded
CUTHAR | Roof screen wall | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-277 | Uploaded
CUTHAR | Commute to Site | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-278 | Uploaded
CUTHAR | Garage Gutters | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-279 | Uploaded
CUTHAR | Paperwork | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-280 | Uploaded
GRETAR | L10 deck panels | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-281 | Uploaded
GRETAR | Column wraps @ podium | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-282 | Uploaded
GRETAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-283 | Uploaded
GRETAR | Wall panels @ entry vestibule | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-284 | Uploaded
GRETAR | Penthouse gutters and DS | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.6 | 6446.0-285 | Uploaded
HANTYL | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-286 | Uploaded
HANTYL | Exterior window installation | 7 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-287 | Uploaded
HANTYL | Facade metal panel installation | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-288 | Uploaded
HANTYL | Basement waterproofing | 7.5 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-289 | Uploaded
HANTYL | Elevator shaft framing | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-290 | Uploaded
JOHSCO | Site drainage installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-291 | Uploaded
JOHSCO | Concrete foundation pouring | 4 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-292 | Uploaded
JOHSCO | HVAC ductwork installation | 4 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-293 | Uploaded
JOHSCO | Interior wall framing | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-294 | Uploaded
JOHSCO | Electrical conduit installation | 2 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4 | 6446.0-295 | Uploaded
JOHSCO | Fire sprinkler system installation | 6 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-296 | Uploaded
JOHSCO | Roof membrane installation | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.2 | 6446.0-297 | Uploaded
NGUKHA | Floor tile installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-298 | Uploaded
NGUKHA | Drywall installation | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.7 | 6446.0-299 | Uploaded
NGUKHA | Parking lot asphalt paving | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-300 | Uploaded
NGUKHA | Landscape irrigation installation | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-301 | Uploaded
NGUKHA | Structural steel erection | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-302 | Uploaded
OETBRO | Guardrail installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-303 | Uploaded
OETBRO | Exterior painting | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-304 | Uploaded
OETBRO | Interior door installation | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-305 | Uploaded
OETBRO | Window caulking and sealing | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-306 | Uploaded
OETBRO | Ceiling grid installation | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-307 | Uploaded
OSBKEV | Building insulation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-308 | Uploaded
OSBKEV | Hardwood flooring installation | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-309 | Uploaded
OSBKEV | Crown molding installation | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-310 | Uploaded
OSBKEV | Kitchen cabinetry installation | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-311 | Uploaded
OSBKEV | Bathroom fixture installation | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-312 | Uploaded
SLOKYL | Tool organization | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-313 | Uploaded
SLOKYL | Team safety meeting | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-314 | Uploaded
SLOKYL | Material delivery coordination | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.3 | 6446.0-315 | Uploaded
SLOKYL | Quality control inspection | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-316 | Uploaded
SLOKYL | Stair railing installation | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-317 | Uploaded
STEJAC | Building permit processing | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-318 | Uploaded
STEJAC | Demolition work | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-319 | Uploaded
STEJAC | Scaffolding assembly | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-320 | Uploaded
STEJAC | Masonry wall construction | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-321 | Uploaded
STEJAC | Plumbing rough-in | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-322 | Uploaded
WISJER | Exterior lighting installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-323 | Uploaded
WISJER | Rooftop HVAC unit installation | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-324 | Uploaded
WISJER | Subcontractor coordination | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-325 | Uploaded
WISJER | Curtain wall installation | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-326 | Uploaded
WISJER | Balcony waterproofing | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-327 | Uploaded
BROAUS | Emergency exit signage installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-328 | Uploaded
BAUTHA | Project planning and scheduling | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-329 | Uploaded
JACJOH | Security system wiring | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-330 | Uploaded
CAVJAM | Penthouse siding and coping | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-331 | Uploaded
BROAUS | Roof screen wall | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-332 | Uploaded
BAUTHA | Commute to Site | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-333 | Uploaded
JACJOH | Garage Gutters | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.81 | 6446.0-334 | Uploaded
CAVJAM | Paperwork | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-335 | Uploaded
BROAUS | L10 deck panels | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-336 | Uploaded
BAUTHA | Column wraps @ podium | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-337 | Uploaded
JACJOH | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-338 | Uploaded
BROAUS | Wall panels @ entry vestibule | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-339 | Uploaded
BAUTHA | Penthouse gutters and DS | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-340 | Uploaded
JACJOH | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-341 | Uploaded
CAVJAM | Exterior window installation | 3 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-342 | Uploaded
CAVJAM | Facade metal panel installation | 5 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-343 | Uploaded
BROAUS | Basement waterproofing | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.9 | 6446.0-344 | Uploaded
BAUTHA | Elevator shaft framing | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-345 | Uploaded
JACJOH | Site drainage installation | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-346 | Uploaded
CAVJAM | Concrete foundation pouring | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-347 | Uploaded
ATWAVO | HVAC ductwork installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-348 | Uploaded
NGUKHA | Interior wall framing | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-349 | Uploaded
GRECHR | Electrical conduit installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-350 | Uploaded
QUINJR | Fire sprinkler system installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-351 | Uploaded
QUITIT | Roof membrane installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-352 | Uploaded
CUTHAR | Floor tile installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-353 | Uploaded
BENDAN | Drywall installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-354 | Uploaded
CHAJAV | Parking lot asphalt paving | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-355 | Uploaded
HANTYL | Landscape irrigation installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-356 | Uploaded
CUSCAR | Structural steel erection | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.7 | 6446.0-357 | Uploaded
BROAUS | Guardrail installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-358 | Uploaded
BAUTHA | Exterior painting | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-359 | Uploaded
JAMNIC | Interior door installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-360 | Uploaded
CAMPHI | Window caulking and sealing | 6 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-361 | Uploaded
WISJER | Ceiling grid installation | 0.5 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-362 | Uploaded
WISJER | Building insulation | 7.5 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-363 | Uploaded
JACJOH | Hardwood flooring installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-364 | Uploaded
GRETAR | Crown molding installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-365 | Uploaded
CAVJAM | Kitchen cabinetry installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-366 | Uploaded
JOHSCO | Bathroom fixture installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-367 | Uploaded
ATWAVO | Tool organization | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-368 | Uploaded
NGUKHA | Team safety meeting | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6 | 6446.0-369 | Uploaded
OSBKEV | Material delivery coordination | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4 | 6446.0-370 | Uploaded
QUINJR | Quality control inspection | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-371 | Uploaded
QUITIT | Stair railing installation | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-372 | Uploaded
CUTHAR | Building permit processing | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-373 | Uploaded
BENDAN | Demolition work | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.6 | 6446.0-374 | Uploaded
CHAJAV | Scaffolding assembly | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-375 | Uploaded
HANTYL | Masonry wall construction | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.1 | 6446.0-376 | Uploaded
CUSCAR | Plumbing rough-in | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-377 | Uploaded
BROAUS | Exterior lighting installation | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-378 | Uploaded
BAUTHA | Rooftop HVAC unit installation | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-379 | Uploaded
JAMNIC | Subcontractor coordination | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-380 | Uploaded
CAMPHI | Curtain wall installation | 3 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-381 | Uploaded
CAMPHI | Balcony waterproofing | 5 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-382 | Uploaded
WISJER | Emergency exit signage installation | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-383 | Uploaded
JACJOH | Project planning and scheduling | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-384 | Uploaded
GRETAR | Security system wiring | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-385 | Uploaded
CAVJAM | Penthouse siding and coping | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-386 | Uploaded
JOHSCO | Roof screen wall | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-387 | Uploaded
ATWAVO | Commute to Site | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-388 | Uploaded
NGUKHA | Garage Gutters | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.6 | 6446.0-389 | Uploaded
OSBKEV | Paperwork | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-390 | Uploaded
QUINJR | L10 deck panels | 3 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.7 | 6446.0-391 | Uploaded
QUINJR | Column wraps @ podium | 5 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-392 | Uploaded
QUITIT | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-393 | Uploaded
CUTHAR | Wall panels @ entry vestibule | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-394 | Uploaded
BENDAN | Penthouse gutters and DS | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-395 | Uploaded
CHAJAV | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-396 | Uploaded
HANTYL | Exterior window installation | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-397 | Uploaded
CUSCAR | Facade metal panel installation | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.7 | 6446.0-398 | Uploaded
BAUTHA | Basement waterproofing | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-399 | Uploaded
JAMNIC | Elevator shaft framing | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.1 | 6446.0-400 | Uploaded
CAMPHI | Site drainage installation | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-401 | Uploaded
WISJER | Concrete foundation pouring | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.8 | 6446.0-402 | Uploaded
JACJOH | HVAC ductwork installation | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-403 | Uploaded
GRETAR | Interior wall framing | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-404 | Uploaded
CAVJAM | Electrical conduit installation | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-405 | Uploaded
JOHSCO | Fire sprinkler system installation | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-406 | Uploaded
ATWAVO | Roof membrane installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-407 | Uploaded
NGUKHA | Floor tile installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-408 | Uploaded
OETBRO | Drywall installation | 3 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-409 | Uploaded
OSBKEV | Parking lot asphalt paving | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-410 | Uploaded
QUINJR | Landscape irrigation installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-411 | Uploaded
QUITIT | Structural steel erection | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-412 | Uploaded
CUTHAR | Guardrail installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-413 | Uploaded
BENDAN | Exterior painting | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-414 | Uploaded
CHAJAV | Interior door installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-415 | Uploaded
HANTYL | Window caulking and sealing | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-416 | Uploaded
CUSCAR | Ceiling grid installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-417 | Uploaded
BROAUS | Building insulation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-418 | Uploaded
BAUTHA | Hardwood flooring installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-419 | Uploaded
JAMNIC | Crown molding installation | 5 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-420 | Uploaded
CAMPHI | Kitchen cabinetry installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-421 | Uploaded
WISJER | Bathroom fixture installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-422 | Uploaded
JACJOH | Tool organization | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-423 | Uploaded
GRETAR | Team safety meeting | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-424 | Uploaded
CAVJAM | Material delivery coordination | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6 | 6446.0-425 | Uploaded
JOHSCO | Quality control inspection | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-426 | Uploaded
ATWAVO | Stair railing installation | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-427 | Uploaded
NGUKHA | Building permit processing | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-428 | Uploaded
GRECHR | Demolition work | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-429 | Uploaded
OETBRO | Scaffolding assembly | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.9 | 6446.0-430 | Uploaded
OSBKEV | Masonry wall construction | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.9 | 6446.0-431 | Uploaded
QUINJR | Plumbing rough-in | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-432 | Uploaded
QUITIT | Exterior lighting installation | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-433 | Uploaded
CUTHAR | Rooftop HVAC unit installation | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-434 | Uploaded
BENDAN | Subcontractor coordination | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-435 | Uploaded
CHAJAV | Curtain wall installation | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-436 | Uploaded
PARBRY | Balcony waterproofing | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-437 | Uploaded
SMICHA | Emergency exit signage installation | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-438 | Uploaded
MACDOU | Project planning and scheduling | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-439 | Uploaded
HANTYL | Security system wiring | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-440 | Uploaded
CUSCAR | Penthouse siding and coping | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-441 | Uploaded
BROAUS | Roof screen wall | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-442 | Uploaded
BAUTHA | Commute to Site | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-443 | Uploaded
JAMNIC | Garage Gutters | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.9 | 6446.0-444 | Uploaded
CAMPHI | Paperwork | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-445 | Uploaded
WISJER | L10 deck panels | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-446 | Uploaded
JACJOH | Column wraps @ podium | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-447 | Uploaded
GRETAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-448 | Uploaded
CAVJAM | Wall panels @ entry vestibule | 7 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-449 | Uploaded
CAVJAM | Penthouse gutters and DS | 1 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-450 | Uploaded
JOHSCO | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-451 | Uploaded
GRECHR | Exterior window installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-452 | Uploaded
OETBRO | Facade metal panel installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-453 | Uploaded
OSBKEV | Basement waterproofing | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.2 | 6446.0-454 | Uploaded
QUINJR | Elevator shaft framing | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-455 | Uploaded
QUITIT | Site drainage installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1 | 6446.0-456 | Uploaded
CUTHAR | Concrete foundation pouring | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-457 | Uploaded
BENDAN | HVAC ductwork installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-458 | Uploaded
CHAJAV | Interior wall framing | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.8 | 6446.0-459 | Uploaded
PARBRY | Electrical conduit installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-460 | Uploaded
SMICHA | Fire sprinkler system installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-461 | Uploaded
MACDOU | Roof membrane installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-462 | Uploaded
HANTYL | Floor tile installation | 3 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-463 | Uploaded
HANTYL | Drywall installation | 5 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-464 | Uploaded
CUSCAR | Parking lot asphalt paving | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-465 | Uploaded
SLOKYL | Landscape irrigation installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-466 | Uploaded
BROAUS | Structural steel erection | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-467 | Uploaded
BAUTHA | Guardrail installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-468 | Uploaded
JAMNIC | Exterior painting | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-469 | Uploaded
CAMPHI | Interior door installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-470 | Uploaded
WISJER | Window caulking and sealing | 3 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-471 | Uploaded
WISJER | Ceiling grid installation | 5 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-472 | Uploaded
STEJAC | Building insulation | 3 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-473 | Uploaded
STEJAC | Hardwood flooring installation | 5 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-474 | Uploaded
JACJOH | Crown molding installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-475 | Uploaded
GRETAR | Kitchen cabinetry installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-476 | Uploaded
CAVJAM | Bathroom fixture installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.9 | 6446.0-477 | Uploaded
JOHSCO | Tool organization | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-478 | Uploaded
OETBRO | Team safety meeting | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-479 | Uploaded
OSBKEV | Material delivery coordination | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-480 | Uploaded
QUINJR | Quality control inspection | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-481 | Uploaded
QUITIT | Stair railing installation | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-482 | Uploaded
CUTHAR | Building permit processing | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-483 | Uploaded
BENDAN | Demolition work | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-484 | Uploaded
CHAJAV | Scaffolding assembly | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.9 | 6446.0-485 | Uploaded
PARBRY | Masonry wall construction | 7.5 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-486 | Uploaded
SMICHA | Plumbing rough-in | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-487 | Uploaded
MACDOU | Exterior lighting installation | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-488 | Uploaded
HANTYL | Rooftop HVAC unit installation | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-489 | Uploaded
CUSCAR | Subcontractor coordination | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-490 | Uploaded
SLOKYL | Curtain wall installation | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-491 | Uploaded
CATMAT | Balcony waterproofing | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-492 | Uploaded
BROAUS | Emergency exit signage installation | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-493 | Uploaded
BAUTHA | Project planning and scheduling | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-494 | Uploaded
JAMNIC | Security system wiring | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-495 | Uploaded
CAMPHI | Penthouse siding and coping | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.9 | 6446.0-496 | Uploaded
WISJER | Roof screen wall | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4 | 6446.0-497 | Uploaded
STEJAC | Commute to Site | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.2 | 6446.0-498 | Uploaded
JACJOH | Garage Gutters | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-499 | Uploaded
GRETAR | Paperwork | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-500 | Uploaded
CAVJAM | L10 deck panels | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-501 | Uploaded
JOHSCO | Column wraps @ podium | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-502 | Uploaded
OETBRO | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-503 | Uploaded
OSBKEV | Wall panels @ entry vestibule | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-504 | Uploaded
QUINJR | Penthouse gutters and DS | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-505 | Uploaded
QUITIT | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-506 | Uploaded
CUTHAR | Exterior window installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-507 | Uploaded
BENDAN | Facade metal panel installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-508 | Uploaded
CHAJAV | Basement waterproofing | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-509 | Uploaded
PARBRY | Elevator shaft framing | 4 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-510 | Uploaded
PARBRY | Site drainage installation | 4 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-511 | Uploaded
SMICHA | Concrete foundation pouring | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.1 | 6446.0-512 | Uploaded
MACDOU | HVAC ductwork installation | 4 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4 | 6446.0-513 | Uploaded
MACDOU | Interior wall framing | 4 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-514 | Uploaded
CUSCAR | Electrical conduit installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-515 | Uploaded
SLOKYL | Fire sprinkler system installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-516 | Uploaded
CATMAT | Roof membrane installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-517 | Uploaded
BROAUS | Floor tile installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-518 | Uploaded
BAUTHA | Drywall installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-519 | Uploaded
JAMNIC | Parking lot asphalt paving | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-520 | Uploaded
CAMPHI | Landscape irrigation installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-521 | Uploaded
WISJER | Structural steel erection | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-522 | Uploaded
STEJAC | Guardrail installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-523 | Uploaded
JACJOH | Exterior painting | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.9 | 6446.0-524 | Uploaded
GRETAR | Interior door installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-525 | Uploaded
CAVJAM | Window caulking and sealing | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-526 | Uploaded
JOHSCO | Ceiling grid installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-527 | Uploaded
LUCLAW | Building insulation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-528 | Uploaded
OETBRO | Hardwood flooring installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-529 | Uploaded
OSBKEV | Crown molding installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-530 | Uploaded
QUINJR | Kitchen cabinetry installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-531 | Uploaded
QUITIT | Bathroom fixture installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-532 | Uploaded
CUTHAR | Tool organization | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.2 | 6446.0-533 | Uploaded
CHAJAV | Team safety meeting | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-534 | Uploaded
PARBRY | Material delivery coordination | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-535 | Uploaded
SMICHA | Quality control inspection | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-536 | Uploaded
MACDOU | Stair railing installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-537 | Uploaded
HANTYL | Building permit processing | 7.5 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-538 | Uploaded
CUSCAR | Demolition work | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-539 | Uploaded
SLOKYL | Scaffolding assembly | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-540 | Uploaded
CATMAT | Masonry wall construction | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-541 | Uploaded
BROAUS | Plumbing rough-in | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.6 | 6446.0-542 | Uploaded
BAUTHA | Exterior lighting installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-543 | Uploaded
JAMNIC | Rooftop HVAC unit installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-544 | Uploaded
CAMPHI | Subcontractor coordination | 3 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-545 | Uploaded
CAMPHI | Curtain wall installation | 5 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-546 | Uploaded
WISJER | Balcony waterproofing | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-547 | Uploaded
STEJAC | Emergency exit signage installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-548 | Uploaded
JACJOH | Project planning and scheduling | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-549 | Uploaded
GRETAR | Security system wiring | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-550 | Uploaded
CAVJAM | Penthouse siding and coping | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-551 | Uploaded
JOHSCO | Roof screen wall | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-552 | Uploaded
LUCLAW | Commute to Site | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-553 | Uploaded
OETBRO | Garage Gutters | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-554 | Uploaded
OSBKEV | Paperwork | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-555 | Uploaded
QUINJR | L10 deck panels | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-556 | Uploaded
QUITIT | Column wraps @ podium | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-557 | Uploaded
CUTHAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-558 | Uploaded
CHAJAV | Wall panels @ entry vestibule | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-559 | Uploaded
PARBRY | Penthouse gutters and DS | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-560 | Uploaded
SMICHA | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-561 | Uploaded
MACDOU | Exterior window installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-562 | Uploaded
HANTYL | Facade metal panel installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-563 | Uploaded
CUSCAR | Basement waterproofing | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-564 | Uploaded
SLOKYL | Elevator shaft framing | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-565 | Uploaded
CATMAT | Site drainage installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-566 | Uploaded
BROAUS | Concrete foundation pouring | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-567 | Uploaded
JAMNIC | HVAC ductwork installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-568 | Uploaded
CAMPHI | Interior wall framing | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-569 | Uploaded
WISJER | Electrical conduit installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-570 | Uploaded
STEJAC | Fire sprinkler system installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-571 | Uploaded
JACJOH | Roof membrane installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.2 | 6446.0-572 | Uploaded
GRETAR | Floor tile installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.7 | 6446.0-573 | Uploaded
CAVJAM | Drywall installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-574 | Uploaded
JOHSCO | Parking lot asphalt paving | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-575 | Uploaded
LUCLAW | Landscape irrigation installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-576 | Uploaded
OETBRO | Structural steel erection | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-577 | Uploaded
OSBKEV | Guardrail installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-578 | Uploaded
CUTHAR | Exterior painting | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-579 | Uploaded
CHAJAV | Interior door installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-580 | Uploaded
PARBRY | Window caulking and sealing | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-581 | Uploaded
MACDOU | Ceiling grid installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-582 | Uploaded
HANTYL | Building insulation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-583 | Uploaded
CUSCAR | Hardwood flooring installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-584 | Uploaded
SLOKYL | Crown molding installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-585 | Uploaded
CATMAT | Kitchen cabinetry installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-586 | Uploaded
BROAUS | Bathroom fixture installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-587 | Uploaded
CAMPHI | Tool organization | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-588 | Uploaded
WISJER | Team safety meeting | 3 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-589 | Uploaded
WISJER | Material delivery coordination | 5 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-590 | Uploaded
STEJAC | Quality control inspection | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-591 | Uploaded
JACJOH | Stair railing installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-592 | Uploaded
GRETAR | Building permit processing | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.9 | 6446.0-593 | Uploaded
CAVJAM | Demolition work | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-594 | Uploaded
JOHSCO | Scaffolding assembly | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-595 | Uploaded
OETBRO | Masonry wall construction | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-596 | Uploaded
OSBKEV | Plumbing rough-in | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-597 | Uploaded
CUTHAR | Exterior lighting installation | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-598 | Uploaded
CHAJAV | Rooftop HVAC unit installation | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-599 | Uploaded
PARBRY | Subcontractor coordination | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-600 | Uploaded
MACDOU | Curtain wall installation | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 9 | 6446.0-601 | Uploaded
HANTYL | Balcony waterproofing | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.2 | 6446.0-602 | Uploaded
CUSCAR | Emergency exit signage installation | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-603 | Uploaded
SLOKYL | Project planning and scheduling | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-604 | Uploaded
CATMAT | Security system wiring | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-605 | Uploaded
BROAUS | Penthouse siding and coping | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-606 | Uploaded
CAMPHI | Roof screen wall | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.6 | 6446.0-607 | Uploaded
WISJER | Commute to Site | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-608 | Uploaded
JACJOH | Garage Gutters | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-609 | Uploaded
GRETAR | Paperwork | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-610 | Uploaded
CAVJAM | L10 deck panels | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-611 | Uploaded
JOHSCO | Column wraps @ podium | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.8 | 6446.0-612 | Uploaded
OETBRO | Sheet metal roof @ L14 canopy | 7 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-613 | Uploaded
OSBKEV | Wall panels @ entry vestibule | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-614 | Uploaded
CUTHAR | Penthouse gutters and DS | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-615 | Uploaded
BENDAN | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-616 | Uploaded
CHAJAV | Exterior window installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-617 | Uploaded
PARBRY | Facade metal panel installation | 3 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-618 | Uploaded
PARBRY | Basement waterproofing | 5 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-619 | Uploaded
MACDOU | Elevator shaft framing | 3 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-620 | Uploaded
MACDOU | Site drainage installation | 5 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-621 | Uploaded
HANTYL | Concrete foundation pouring | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-622 | Uploaded
CUSCAR | HVAC ductwork installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-623 | Uploaded
SLOKYL | Interior wall framing | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-624 | Uploaded
CATMAT | Electrical conduit installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-625 | Uploaded
BROAUS | Fire sprinkler system installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-626 | Uploaded
BAUTHA | Roof membrane installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-627 | Uploaded
CAMPHI | Floor tile installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-628 | Uploaded
WISJER | Drywall installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4 | 6446.0-629 | Uploaded
STEJAC | Parking lot asphalt paving | 5.25 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-630 | Uploaded
JACJOH | Landscape irrigation installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-631 | Uploaded
GRETAR | Structural steel erection | 6.5 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-632 | Uploaded
CAVJAM | Guardrail installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-633 | Uploaded
JOHSCO | Exterior painting | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.6 | 6446.0-634 | Uploaded
CUTHAR | Interior door installation | 4.5 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-635 | Uploaded
BENDAN | Window caulking and sealing | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-636 | Uploaded
CHAJAV | Ceiling grid installation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-637 | Uploaded
PARBRY | Building insulation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-638 | Uploaded
MACDOU | Hardwood flooring installation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-639 | Uploaded
HANTYL | Crown molding installation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-640 | Uploaded
CUSCAR | Kitchen cabinetry installation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-641 | Uploaded
SLOKYL | Bathroom fixture installation | 3 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-642 | Uploaded
SLOKYL | Tool organization | 5 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-643 | Uploaded
CATMAT | Team safety meeting | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-644 | Uploaded
BROAUS | Material delivery coordination | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-645 | Uploaded
BAUTHA | Quality control inspection | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-646 | Uploaded
JAMNIC | Stair railing installation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-647 | Uploaded
CAMPHI | Building permit processing | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-648 | Uploaded
WISJER | Demolition work | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-649 | Uploaded
STEJAC | Scaffolding assembly | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-650 | Uploaded
JACJOH | Masonry wall construction | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.8 | 6446.0-651 | Uploaded
GRETAR | Plumbing rough-in | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-652 | Uploaded
CAVJAM | Exterior lighting installation | 1.75 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 9 | 6446.0-653 | Uploaded
JOHSCO | Rooftop HVAC unit installation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.7 | 6446.0-654 | Uploaded
QUINJR | Subcontractor coordination | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-655 | Uploaded
QUITIT | Curtain wall installation | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-656 | Uploaded
CUTHAR | Balcony waterproofing | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-657 | Uploaded
BENDAN | Emergency exit signage installation | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-658 | Uploaded
CHAJAV | Project planning and scheduling | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-659 | Uploaded
PARBRY | Security system wiring | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-660 | Uploaded
SMICHA | Penthouse siding and coping | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-661 | Uploaded
MACDOU | Roof screen wall | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-662 | Uploaded
HANTYL | Commute to Site | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-663 | Uploaded
CUSCAR | Garage Gutters | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-664 | Uploaded
SLOKYL | Paperwork | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-665 | Uploaded
CATMAT | L10 deck panels | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-666 | Uploaded
BROAUS | Column wraps @ podium | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-667 | Uploaded
BAUTHA | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-668 | Uploaded
JAMNIC | Wall panels @ entry vestibule | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-669 | Uploaded
CAMPHI | Penthouse gutters and DS | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-670 | Uploaded
WISJER | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-671 | Uploaded
STEJAC | Exterior window installation | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-672 | Uploaded
JACJOH | Facade metal panel installation | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-673 | Uploaded
GRETAR | Basement waterproofing | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-674 | Uploaded
CAVJAM | Elevator shaft framing | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-675 | Uploaded
JOHSCO | Site drainage installation | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-676 | Uploaded
LUCLAW | Concrete foundation pouring | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-677 | Uploaded
QUINJR | HVAC ductwork installation | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-678 | Uploaded
QUITIT | Interior wall framing | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-679 | Uploaded
BENDAN | Electrical conduit installation | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-680 | Uploaded
CHAJAV | Fire sprinkler system installation | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-681 | Uploaded
PARBRY | Roof membrane installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-682 | Uploaded
SMICHA | Floor tile installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-683 | Uploaded
MACDOU | Drywall installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.4 | 6446.0-684 | Uploaded
HANTYL | Parking lot asphalt paving | 4 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-685 | Uploaded
HANTYL | Landscape irrigation installation | 4 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-686 | Uploaded
CUSCAR | Structural steel erection | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.3 | 6446.0-687 | Uploaded
SLOKYL | Guardrail installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-688 | Uploaded
CATMAT | Exterior painting | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-689 | Uploaded
BROAUS | Interior door installation | 5 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-690 | Uploaded
BAUTHA | Window caulking and sealing | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-691 | Uploaded
JAMNIC | Ceiling grid installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-692 | Uploaded
CAMPHI | Building insulation | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-693 | Uploaded
WISJER | Hardwood flooring installation | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-694 | Uploaded
STEJAC | Crown molding installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-695 | Uploaded
JACJOH | Kitchen cabinetry installation | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-696 | Uploaded
CAVJAM | Bathroom fixture installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-697 | Uploaded
JOHSCO | Tool organization | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-698 | Uploaded
QUINJR | Team safety meeting | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.9 | 6446.0-699 | Uploaded
QUITIT | Material delivery coordination | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-700 | Uploaded
BENDAN | Quality control inspection | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-701 | Uploaded
CHAJAV | Stair railing installation | 2 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-702 | Uploaded
CHAJAV | Building permit processing | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-703 | Uploaded
PARBRY | Demolition work | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-704 | Uploaded
HANTYL | Scaffolding assembly | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-705 | Uploaded
CUSCAR | Masonry wall construction | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-706 | Uploaded
SLOKYL | Plumbing rough-in | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-707 | Uploaded
CATMAT | Exterior lighting installation | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-708 | Uploaded
BROAUS | Rooftop HVAC unit installation | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-709 | Uploaded
BAUTHA | Subcontractor coordination | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-710 | Uploaded
JAMNIC | Curtain wall installation | 6.5 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-711 | Uploaded
CAMPHI | Balcony waterproofing | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-712 | Uploaded
STEJAC | Emergency exit signage installation | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-713 | Uploaded
JACJOH | Project planning and scheduling | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-714 | Uploaded
CAVJAM | Security system wiring | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-715 | Uploaded
JOHSCO | Penthouse siding and coping | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-716 | Uploaded
LUCLAW | Roof screen wall | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-717 | Uploaded
QUINJR | Commute to Site | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-718 | Uploaded
QUITIT | Garage Gutters | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-719 | Uploaded
BENDAN | Paperwork | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-720 | Uploaded
CHAJAV | L10 deck panels | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-721 | Uploaded
PARBRY | Column wraps @ podium | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-722 | Uploaded
HANTYL | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-723 | Uploaded
CUSCAR | Wall panels @ entry vestibule | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-724 | Uploaded
SLOKYL | Penthouse gutters and DS | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-725 | Uploaded
CATMAT | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-726 | Uploaded
BROAUS | Exterior window installation | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.1 | 6446.0-727 | Uploaded
BAUTHA | Facade metal panel installation | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-728 | Uploaded
JAMNIC | Basement waterproofing | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-729 | Uploaded
CAMPHI | Elevator shaft framing | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-730 | Uploaded
STEJAC | Site drainage installation | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-731 | Uploaded
JACJOH | Concrete foundation pouring | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-732 | Uploaded
CAVJAM | HVAC ductwork installation | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.1 | 6446.0-733 | Uploaded
JOHSCO | Interior wall framing | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-734 | Uploaded
QUINJR | Electrical conduit installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-735 | Uploaded
QUITIT | Fire sprinkler system installation | 8 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-736 | Uploaded
BENDAN | Roof membrane installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-737 | Uploaded
CHAJAV | Floor tile installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.9 | 6446.0-738 | Uploaded
SMICHA | Drywall installation | 8 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.4 | 6446.0-739 | Uploaded
MACDOU | Parking lot asphalt paving | 8 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-740 | Uploaded
HANTYL | Landscape irrigation installation | 8 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-741 | Uploaded
CUSCAR | Structural steel erection | 8 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-742 | Uploaded
SLOKYL | Guardrail installation | 8 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-743 | Uploaded
CATMAT | Exterior painting | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-744 | Uploaded
BROAUS | Interior door installation | 7.5 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-745 | Uploaded
BAUTHA | Window caulking and sealing | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-746 | Uploaded
JAMNIC | Ceiling grid installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-747 | Uploaded
CAMPHI | Building insulation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-748 | Uploaded
STEJAC | Hardwood flooring installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-749 | Uploaded
JACJOH | Crown molding installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-750 | Uploaded
CAVJAM | Kitchen cabinetry installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.9 | 6446.0-751 | Uploaded
JOHSCO | Bathroom fixture installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-752 | Uploaded
OETBRO | Tool organization | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-753 | Uploaded
QUITIT | Team safety meeting | 6.5 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-754 | Uploaded
CUTHAR | Material delivery coordination | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-755 | Uploaded
BENDAN | Quality control inspection | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-756 | Uploaded
CHAJAV | Stair railing installation | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-757 | Uploaded
PARBRY | Building permit processing | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.7 | 6446.0-758 | Uploaded
SMICHA | Demolition work | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-759 | Uploaded
HANTYL | Scaffolding assembly | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-760 | Uploaded
CUSCAR | Masonry wall construction | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.3 | 6446.0-761 | Uploaded
SLOKYL | Plumbing rough-in | 5 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-762 | Uploaded
CATMAT | Exterior lighting installation | 1.5 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-763 | Uploaded
BROAUS | Rooftop HVAC unit installation | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-764 | Uploaded
BAUTHA | Subcontractor coordination | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-765 | Uploaded
JAMNIC | Curtain wall installation | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-766 | Uploaded
WISJER | Balcony waterproofing | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1 | 6446.0-767 | Uploaded
STEJAC | Emergency exit signage installation | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-768 | Uploaded
GRETAR | Project planning and scheduling | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1 | 6446.0-769 | Uploaded
JOHSCO | Security system wiring | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-770 | Uploaded
QUITIT | Penthouse siding and coping | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-771 | Uploaded
CUTHAR | Roof screen wall | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-772 | Uploaded
BENDAN | Commute to Site | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-773 | Uploaded
CHAJAV | Garage Gutters | 1 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-774 | Uploaded
CHAJAV | Paperwork | 7 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-775 | Uploaded
PARBRY | L10 deck panels | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-776 | Uploaded
SMICHA | Column wraps @ podium | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-777 | Uploaded
CUSCAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.4 | 6446.0-778 | Uploaded
SLOKYL | Wall panels @ entry vestibule | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-779 | Uploaded
JAMNIC | Penthouse gutters and DS | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-780 | Uploaded
WISJER | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-781 | Uploaded
STEJAC | Exterior window installation | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-782 | Uploaded
GRETAR | Facade metal panel installation | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-783 | Uploaded
JOHSCO | Basement waterproofing | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-784 | Uploaded
QUITIT | Elevator shaft framing | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-785 | Uploaded
CUTHAR | Site drainage installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.9 | 6446.0-786 | Uploaded
BENDAN | Concrete foundation pouring | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-787 | Uploaded
CHAJAV | HVAC ductwork installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-788 | Uploaded
PARBRY | Interior wall framing | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-789 | Uploaded
SMICHA | Electrical conduit installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-790 | Uploaded
MACDOU | Fire sprinkler system installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-791 | Uploaded
HANTYL | Roof membrane installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-792 | Uploaded
CUSCAR | Floor tile installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-793 | Uploaded
SLOKYL | Drywall installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-794 | Uploaded
CATMAT | Parking lot asphalt paving | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-795 | Uploaded
BROAUS | Landscape irrigation installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-796 | Uploaded
BAUTHA | Structural steel erection | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-797 | Uploaded
CAMPHI | Guardrail installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-798 | Uploaded
WISJER | Exterior painting | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-799 | Uploaded
STEJAC | Interior door installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-800 | Uploaded
JACJOH | Window caulking and sealing | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-801 | Uploaded
GRETAR | Ceiling grid installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-802 | Uploaded
CAVJAM | Building insulation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-803 | Uploaded
JOHSCO | Hardwood flooring installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-804 | Uploaded
SMICHA | Crown molding installation | 2 |  | 2024-05-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-805 | Uploaded
JOHSCO | Kitchen cabinetry installation | 2 |  | 2024-05-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-806 | Uploaded
LUCLAW | Bathroom fixture installation | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-807 | Uploaded
QUITIT | Tool organization | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-808 | Uploaded
CUTHAR | Team safety meeting | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-809 | Uploaded
BENDAN | Material delivery coordination | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-810 | Uploaded
CHAJAV | Quality control inspection | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-811 | Uploaded
PARBRY | Stair railing installation | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-812 | Uploaded
SMICHA | Building permit processing | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-813 | Uploaded
MACDOU | Demolition work | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-814 | Uploaded
HANTYL | Scaffolding assembly | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-815 | Uploaded
CUSCAR | Masonry wall construction | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-816 | Uploaded
SLOKYL | Plumbing rough-in | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-817 | Uploaded
CATMAT | Exterior lighting installation | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.2 | 6446.0-818 | Uploaded
BROAUS | Rooftop HVAC unit installation | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-819 | Uploaded
BAUTHA | Subcontractor coordination | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.2 | 6446.0-820 | Uploaded
JAMNIC | Curtain wall installation | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-821 | Uploaded
CAMPHI | Balcony waterproofing | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-822 | Uploaded
WISJER | Emergency exit signage installation | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-823 | Uploaded
STEJAC | Project planning and scheduling | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-824 | Uploaded
JACJOH | Security system wiring | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.2 | 6446.0-825 | Uploaded
GRETAR | Penthouse siding and coping | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-826 | Uploaded
CAVJAM | Roof screen wall | 2.5 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-827 | Uploaded
JOHSCO | Commute to Site | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-828 | Uploaded
BURAAR | Garage Gutters |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-829 | Uploaded
COUMAR | Paperwork |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-830 | Uploaded
HENAUS | L10 deck panels |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-831 | Uploaded
CUTHAR | Column wraps @ podium |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-832 | Uploaded
BENDAN | Sheet metal roof @ L14 canopy |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-833 | Uploaded
CHAJAV | Wall panels @ entry vestibule |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-834 | Uploaded
OETBRO | Penthouse gutters and DS |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-835 | Uploaded
SLOKYL | Sheet metal roof @ L14 canopy (roof build up) |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-836 | Uploaded
CATMAT | Exterior window installation |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-837 | Uploaded
BROAUS | Facade metal panel installation |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-838 | Uploaded
JACJOH | Basement waterproofing |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-839 | Uploaded
GRETAR | Elevator shaft framing |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-840 | Uploaded
CAVJAM | Site drainage installation |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-841 | Uploaded
JOHSCO | Concrete foundation pouring |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-842 | Uploaded
CUTHAR | HVAC ductwork installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-843 | Uploaded
BENDAN | Interior wall framing | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-844 | Uploaded
CHAJAV | Electrical conduit installation | 3 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-845 | Uploaded
CHAJAV | Fire sprinkler system installation | 5 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.4 | 6446.0-846 | Uploaded
PARBRY | Roof membrane installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-847 | Uploaded
SMICHA | Floor tile installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-848 | Uploaded
MACDOU | Drywall installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-849 | Uploaded
HANTYL | Parking lot asphalt paving | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-850 | Uploaded
CUSCAR | Landscape irrigation installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-851 | Uploaded
SLOKYL | Structural steel erection | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-852 | Uploaded
CATMAT | Guardrail installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-853 | Uploaded
BROAUS | Exterior painting | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-854 | Uploaded
BAUTHA | Interior door installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-855 | Uploaded
JAMNIC | Window caulking and sealing | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-856 | Uploaded
CAMPHI | Ceiling grid installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-857 | Uploaded
WISJER | Building insulation | 3 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-858 | Uploaded
WISJER | Hardwood flooring installation | 5 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-859 | Uploaded
STEJAC | Crown molding installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-860 | Uploaded
JACJOH | Kitchen cabinetry installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-861 | Uploaded
GRETAR | Bathroom fixture installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-862 | Uploaded
CAVJAM | Tool organization | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-863 | Uploaded
JOHSCO | Team safety meeting | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-864 | Uploaded
QUINJR | Material delivery coordination | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-865 | Uploaded
QUITIT | Quality control inspection | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-866 | Uploaded
CUTHAR | Stair railing installation | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-867 | Uploaded
BENDAN | Building permit processing | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-868 | Uploaded
CHAJAV | Demolition work | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-869 | Uploaded
LUCLAW | Scaffolding assembly | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-870 | Uploaded
PARBRY | Masonry wall construction | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.9 | 6446.0-871 | Uploaded
SMICHA | Plumbing rough-in | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-872 | Uploaded
GRECHR | Exterior lighting installation | 4 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-873 | Uploaded
OSBKEV | Rooftop HVAC unit installation | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.6 | 6446.0-874 | Uploaded
MACDOU | Subcontractor coordination | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-875 | Uploaded
OETBRO | Curtain wall installation | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-876 | Uploaded
HANTYL | Balcony waterproofing | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-877 | Uploaded
CUSCAR | Emergency exit signage installation | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-878 | Uploaded
SLOKYL | Project planning and scheduling | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-879 | Uploaded
CATMAT | Security system wiring | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-880 | Uploaded
BROAUS | Penthouse siding and coping | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-881 | Uploaded
BAUTHA | Roof screen wall | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-882 | Uploaded
JAMNIC | Commute to Site | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-883 | Uploaded
CAMPHI | Garage Gutters | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-884 | Uploaded
WISJER | Paperwork | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.9 | 6446.0-885 | Uploaded
STEJAC | L10 deck panels | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-886 | Uploaded
JACJOH | Column wraps @ podium | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-887 | Uploaded
GRETAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-888 | Uploaded
CAVJAM | Wall panels @ entry vestibule | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-889 | Uploaded
JOHSCO | Penthouse gutters and DS | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-890 | Uploaded
QUINJR | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-891 | Uploaded
QUITIT | Exterior window installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-892 | Uploaded
CUTHAR | Facade metal panel installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-893 | Uploaded
BENDAN | Basement waterproofing | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-894 | Uploaded
CHAJAV | Elevator shaft framing | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-895 | Uploaded
LUCLAW | Site drainage installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-896 | Uploaded
PARBRY | Concrete foundation pouring | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-897 | Uploaded
SMICHA | HVAC ductwork installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-898 | Uploaded
OSBKEV | Interior wall framing | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-899 | Uploaded
MACDOU | Electrical conduit installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-900 | Uploaded
OETBRO | Fire sprinkler system installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-901 | Uploaded
HANTYL | Roof membrane installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-902 | Uploaded
CUSCAR | Floor tile installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-903 | Uploaded
SLOKYL | Drywall installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-904 | Uploaded
CATMAT | Parking lot asphalt paving | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-905 | Uploaded
BROAUS | Landscape irrigation installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.4 | 6446.0-906 | Uploaded
BAUTHA | Structural steel erection | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-907 | Uploaded
JAMNIC | Guardrail installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-908 | Uploaded
CAMPHI | Exterior painting | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-909 | Uploaded
WISJER | Interior door installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-910 | Uploaded
STEJAC | Window caulking and sealing | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-911 | Uploaded
JACJOH | Ceiling grid installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-912 | Uploaded
GRETAR | Building insulation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-913 | Uploaded
CAVJAM | Hardwood flooring installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-914 | Uploaded
JOHSCO | Crown molding installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-915 | Uploaded
CUTHAR | Kitchen cabinetry installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-916 | Uploaded
BENDAN | Bathroom fixture installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-917 | Uploaded
CHAJAV | Tool organization | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-918 | Uploaded
LUCLAW | Team safety meeting | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-919 | Uploaded
PARBRY | Material delivery coordination | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-920 | Uploaded
SMICHA | Quality control inspection | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-921 | Uploaded
MACDOU | Stair railing installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.9 | 6446.0-922 | Uploaded
OETBRO | Building permit processing | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-923 | Uploaded
HANTYL | Demolition work | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-924 | Uploaded
CUSCAR | Scaffolding assembly | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.8 | 6446.0-925 | Uploaded
SLOKYL | Masonry wall construction | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-926 | Uploaded
CATMAT | Plumbing rough-in | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-927 | Uploaded
BROAUS | Exterior lighting installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-928 | Uploaded
BAUTHA | Rooftop HVAC unit installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-929 | Uploaded
JAMNIC | Subcontractor coordination | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-930 | Uploaded
CAMPHI | Curtain wall installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-931 | Uploaded
WISJER | Balcony waterproofing | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-932 | Uploaded
STEJAC | Emergency exit signage installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-933 | Uploaded
JACJOH | Project planning and scheduling | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-934 | Uploaded
GRETAR | Security system wiring | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-935 | Uploaded
CAVJAM | Penthouse siding and coping | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-936 | Uploaded
JOHSCO | Roof screen wall | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-937 | Uploaded
CUTHAR | Commute to Site | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 9 | 6446.0-938 | Uploaded
BENDAN | Garage Gutters | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 9 | 6446.0-939 | Uploaded
CHAJAV | Paperwork | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-940 | Uploaded
LUCLAW | L10 deck panels | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-941 | Uploaded
PARBRY | Column wraps @ podium | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-942 | Uploaded
SMICHA | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-943 | Uploaded
MACDOU | Wall panels @ entry vestibule | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-944 | Uploaded
OETBRO | Penthouse gutters and DS | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-945 | Uploaded
HANTYL | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-946 | Uploaded
CUSCAR | Exterior window installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-947 | Uploaded
SLOKYL | Facade metal panel installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6 | 6446.0-948 | Uploaded
CATMAT | Basement waterproofing | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-949 | Uploaded
BROAUS | Elevator shaft framing | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-950 | Uploaded
BAUTHA | Site drainage installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-951 | Uploaded
JAMNIC | Concrete foundation pouring | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-952 | Uploaded
CAMPHI | HVAC ductwork installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-953 | Uploaded
WISJER | Interior wall framing | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-954 | Uploaded
STEJAC | Electrical conduit installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-955 | Uploaded
JACJOH | Fire sprinkler system installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-956 | Uploaded
GRETAR | Roof membrane installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-957 | Uploaded
CAVJAM | Floor tile installation | 7.5 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-958 | Uploaded
JOHSCO | Drywall installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-959 | Uploaded
BURAAR | Parking lot asphalt paving |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-960 | Uploaded
COUMAR | Landscape irrigation installation |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-961 | Uploaded
OETBRO | Structural steel erection |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-962 | Uploaded
BROAUS | Guardrail installation |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-963 | Uploaded
CAMPHI | Exterior painting |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-964 | Uploaded
JACJOH | Interior door installation |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-965 | Uploaded
GRETAR | Window caulking and sealing |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-966 | Uploaded
CAVJAM | Ceiling grid installation |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.9 | 6446.0-967 | Uploaded
JOHSCO | Building insulation |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-968 | Uploaded
PARBRY | Hardwood flooring installation | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-969 | Uploaded
SMICHA | Crown molding installation | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-970 | Uploaded
MACDOU | Kitchen cabinetry installation | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-971 | Uploaded
OETBRO | Bathroom fixture installation | 5 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-972 | Uploaded
HANTYL | Tool organization | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-973 | Uploaded
CUSCAR | Team safety meeting | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-974 | Uploaded
SLOKYL | Material delivery coordination | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-975 | Uploaded
CATMAT | Quality control inspection | 5 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-976 | Uploaded
BROAUS | Stair railing installation | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6 | 6446.0-977 | Uploaded
CAMPHI | Building permit processing | 5 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-978 | Uploaded
WISJER | Demolition work | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-979 | Uploaded
STEJAC | Scaffolding assembly | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-980 | Uploaded
JACJOH | Masonry wall construction | 5 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-981 | Uploaded
GRETAR | Plumbing rough-in | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-982 | Uploaded
CAVJAM | Exterior lighting installation | 5 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-983 | Uploaded
JOHSCO | Rooftop HVAC unit installation | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-984 | Uploaded
PARBRY | Subcontractor coordination | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-985 | Uploaded
SMICHA | Curtain wall installation | 3 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-986 | Uploaded
GRECHR | Balcony waterproofing | 5 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-987 | Uploaded
OSBKEV | Emergency exit signage installation | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-988 | Uploaded
MACDOU | Project planning and scheduling | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-989 | Uploaded
OETBRO | Security system wiring | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-990 | Uploaded
HANTYL | Penthouse siding and coping | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-991 | Uploaded
CUSCAR | Roof screen wall | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-992 | Uploaded
SLOKYL | Commute to Site | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-993 | Uploaded
CATMAT | Garage Gutters | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-994 | Uploaded
BROAUS | Paperwork | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.9 | 6446.0-995 | Uploaded
JAMNIC | L10 deck panels | 7.75 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.1 | 6446.0-996 | Uploaded
CAMPHI | Column wraps @ podium | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-997 | Uploaded
WISJER | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-998 | Uploaded
STEJAC | Wall panels @ entry vestibule | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-999 | Uploaded
JACJOH | Penthouse gutters and DS | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4 | 6446.0-1000 | Uploaded
GRETAR | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-1001 | Uploaded
CAVJAM | Exterior window installation | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-1002 | Uploaded
JOHSCO | Facade metal panel installation | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-1003 | Uploaded
PARBRY | Basement waterproofing | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-1004 | Uploaded
SMICHA | Elevator shaft framing | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.2 | 6446.0-1005 | Uploaded
GRECHR | Site drainage installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-1006 | Uploaded
OSBKEV | Concrete foundation pouring | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.3 | 6446.0-1007 | Uploaded
MACDOU | HVAC ductwork installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1 | 6446.0-1008 | Uploaded
OETBRO | Interior wall framing | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-1009 | Uploaded
HANTYL | Electrical conduit installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.8 | 6446.0-1010 | Uploaded
CUSCAR | Fire sprinkler system installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-1011 | Uploaded
SLOKYL | Roof membrane installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.9 | 6446.0-1012 | Uploaded
BROAUS | Floor tile installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-1013 | Uploaded
JAMNIC | Drywall installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-1014 | Uploaded
CAMPHI | Parking lot asphalt paving | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-1015 | Uploaded
WISJER | Landscape irrigation installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-1016 | Uploaded
STEJAC | Structural steel erection | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-1017 | Uploaded
JACJOH | Guardrail installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6 | 6446.0-1018 | Uploaded
GRETAR | Exterior painting | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-1019 | Uploaded
CAVJAM | Interior door installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.3 | 6446.0-1020 | Uploaded
JOHSCO | Window caulking and sealing | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-1021 | Uploaded
PARBRY | Ceiling grid installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-1022 | Uploaded
SMICHA | Building insulation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-1023 | Uploaded
OSBKEV | Hardwood flooring installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-1024 | Uploaded
MACDOU | Crown molding installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-1025 | Uploaded
OETBRO | Kitchen cabinetry installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-1026 | Uploaded
HANTYL | Bathroom fixture installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 9 | 6446.0-1027 | Uploaded
CUSCAR | Tool organization | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-1028 | Uploaded
SLOKYL | Team safety meeting | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-1029 | Uploaded
BROAUS | Material delivery coordination | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-1030 | Uploaded
JAMNIC | Quality control inspection | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-1031 | Uploaded
CAMPHI | Stair railing installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-1032 | Uploaded
WISJER | Building permit processing | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-1033 | Uploaded
STEJAC | Demolition work | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-1034 | Uploaded
JACJOH | Scaffolding assembly | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-1035 | Uploaded
GRETAR | Masonry wall construction | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-1036 | Uploaded
CAVJAM | Plumbing rough-in | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-1037 | Uploaded
JOHSCO | Exterior lighting installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-1038 | Uploaded
PARBRY | Rooftop HVAC unit installation | 7 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-1039 | Uploaded
SMICHA | Subcontractor coordination | 7 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-1040 | Uploaded
GRECHR | Curtain wall installation | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-1041 | Uploaded
OSBKEV | Balcony waterproofing | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-1042 | Uploaded
MACDOU | Emergency exit signage installation | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-1043 | Uploaded
OETBRO | Project planning and scheduling | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-1044 | Uploaded
HANTYL | Security system wiring | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.2 | 6446.0-1045 | Uploaded
CUSCAR | Penthouse siding and coping | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-1046 | Uploaded
SLOKYL | Roof screen wall | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-1047 | Uploaded
CATMAT | Commute to Site | 1 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-1048 | Uploaded
BROAUS | Garage Gutters | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.2 | 6446.0-1049 | Uploaded
JAMNIC | Paperwork | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-1050 | Uploaded
CAMPHI | L10 deck panels | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-1051 | Uploaded
WISJER | Column wraps @ podium | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-1052 | Uploaded
JACJOH | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1 | 6446.0-1053 | Uploaded
GRETAR | Wall panels @ entry vestibule | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.9 | 6446.0-1054 | Uploaded
CAVJAM | Penthouse gutters and DS | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.7 | 6446.0-1055 | Uploaded
JOHSCO | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-1056 | Uploaded
TRACCO | Exterior window installation |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-1057 | Uploaded
BURAAR | Facade metal panel installation |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-1058 | Uploaded
UTLJOH | Basement waterproofing |  | 6 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-1059 | Uploaded
OETBRO | Elevator shaft framing |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-1060 | Uploaded
CUSCAR | Site drainage installation |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-1061 | Uploaded
BROAUS | Concrete foundation pouring |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-1062 | Uploaded
JACJOH | HVAC ductwork installation |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-1063 | Uploaded
GRETAR | Interior wall framing |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-1064 | Uploaded
JOHSCO | Electrical conduit installation |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-1065 | Uploaded
OSBKEV | Fire sprinkler system installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-1066 | Uploaded
MACDOU | Roof membrane installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-1067 | Uploaded
OETBRO | Floor tile installation | 5 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-1068 | Uploaded
HANTYL | Drywall installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-1069 | Uploaded
CUSCAR | Parking lot asphalt paving | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-1070 | Uploaded
SLOKYL | Landscape irrigation installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-1071 | Uploaded
CATMAT | Structural steel erection | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-1072 | Uploaded
BROAUS | Guardrail installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-1073 | Uploaded
BAUTHA | Exterior painting | 1 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-1074 | Uploaded
BAUTHA | Interior door installation | 7 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-1075 | Uploaded
JAMNIC | Window caulking and sealing | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-1076 | Uploaded
CAMPHI | Ceiling grid installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-1077 | Uploaded
WISJER | Building insulation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-1078 | Uploaded
JACJOH | Hardwood flooring installation | 1.5 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-1079 | Uploaded
JACJOH | Crown molding installation | 6.5 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-1080 | Uploaded
GRETAR | Kitchen cabinetry installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-1081 | Uploaded
CAVJAM | Bathroom fixture installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-1082 | Uploaded
JOHSCO | Tool organization | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-1083 | Uploaded
MACDOU | Team safety meeting | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-1084 | Uploaded
OETBRO | Material delivery coordination | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-1085 | Uploaded
HANTYL | Quality control inspection | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-1086 | Uploaded
CUSCAR | Stair railing installation | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-1087 | Uploaded
SLOKYL | Building permit processing | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-1088 | Uploaded
CATMAT | Demolition work | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-1089 | Uploaded
BROAUS | Scaffolding assembly | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-1090 | Uploaded
BAUTHA | Masonry wall construction | 5 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-1091 | Uploaded
BAUTHA | Plumbing rough-in | 3 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-1092 | Uploaded
JAMNIC | Exterior lighting installation | 3 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-1093 | Uploaded
JAMNIC | Rooftop HVAC unit installation | 5 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-1094 | Uploaded
CAMPHI | Subcontractor coordination | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-1095 | Uploaded
WISJER | Curtain wall installation | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-1096 | Uploaded
JACJOH | Balcony waterproofing | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-1097 | Uploaded
GRETAR | Emergency exit signage installation | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-1098 | Uploaded
CAVJAM | Project planning and scheduling | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6 | 6446.0-1099 | Uploaded
JOHSCO | Security system wiring | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-1100 | Uploaded
MACDOU | Penthouse siding and coping | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-1101 | Uploaded
OETBRO | Roof screen wall | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-1102 | Uploaded
HANTYL | Commute to Site | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-1103 | Uploaded
CUSCAR | Garage Gutters | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-1104 | Uploaded
SLOKYL | Paperwork | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-1105 | Uploaded
CATMAT | L10 deck panels | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-1106 | Uploaded
BROAUS | Column wraps @ podium | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-1107 | Uploaded
BAUTHA | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-1108 | Uploaded
JAMNIC | Wall panels @ entry vestibule | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.3 | 6446.0-1109 | Uploaded
CAMPHI | Penthouse gutters and DS | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-1110 | Uploaded
WISJER | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-1111 | Uploaded
JACJOH | Exterior window installation | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-1112 | Uploaded
GRETAR | Facade metal panel installation | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-1113 | Uploaded
CAVJAM | Basement waterproofing | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-1114 | Uploaded
JOHSCO | Elevator shaft framing | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-1115 | Uploaded
MACDOU | Site drainage installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-1116 | Uploaded
OETBRO | Concrete foundation pouring | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-1117 | Uploaded
HANTYL | HVAC ductwork installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-1118 | Uploaded
CUSCAR | Interior wall framing | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-1119 | Uploaded
SLOKYL | Electrical conduit installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-1120 | Uploaded
CATMAT | Fire sprinkler system installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.9 | 6446.0-1121 | Uploaded
BAUTHA | Roof membrane installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-1122 | Uploaded
JAMNIC | Floor tile installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-1123 | Uploaded
CAMPHI | Drywall installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-1124 | Uploaded
WISJER | Parking lot asphalt paving | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-1125 | Uploaded
JACJOH | Landscape irrigation installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-1126 | Uploaded
GRETAR | Structural steel erection | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-1127 | Uploaded
CAVJAM | Guardrail installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-1128 | Uploaded
JOHSCO | Exterior painting | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-1129 | Uploaded
HANTYL | Interior door installation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-1130 | Uploaded
CUSCAR | Window caulking and sealing | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-1131 | Uploaded
SLOKYL | Ceiling grid installation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-1132 | Uploaded
CATMAT | Building insulation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-1133 | Uploaded
BAUTHA | Hardwood flooring installation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1 | 6446.0-1134 | Uploaded
JAMNIC | Crown molding installation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-1135 | Uploaded
CAMPHI | Kitchen cabinetry installation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-1136 | Uploaded
WISJER | Bathroom fixture installation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-1137 | Uploaded
JACJOH | Tool organization | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-1138 | Uploaded
GRETAR | Team safety meeting | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-1139 | Uploaded
CAVJAM | Material delivery coordination | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.2 | 6446.0-1140 | Uploaded
JOHSCO | Quality control inspection | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-1141 | Uploaded
BURAAR | Stair railing installation |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-1142 | Uploaded
MCNZAC | Building permit processing |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-1143 | Uploaded
TRACCO | Demolition work |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-1144 | Uploaded
UTLJOH | Scaffolding assembly |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-1145 | Uploaded
CUSCAR | Masonry wall construction |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-1146 | Uploaded
SLOKYL | Plumbing rough-in |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-1147 | Uploaded
CATMAT | Exterior lighting installation |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-1148 | Uploaded
BAUTHA | Rooftop HVAC unit installation |  | 6 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-1149 | Uploaded
CAMPHI | Subcontractor coordination |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-1150 | Uploaded
JACJOH | Curtain wall installation |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-1151 | Uploaded
GRETAR | Balcony waterproofing |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-1152 | Uploaded
CAVJAM | Emergency exit signage installation |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-1153 | Uploaded
JOHSCO | Project planning and scheduling |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-1154 | Uploaded
LUCLAW | Security system wiring | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-1155 | Uploaded
HANTYL | Penthouse siding and coping | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.9 | 6446.0-1156 | Uploaded
CUSCAR | Roof screen wall | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.9 | 6446.0-1157 | Uploaded
SLOKYL | Commute to Site | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-1158 | Uploaded
CATMAT | Garage Gutters | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-1159 | Uploaded
BAUTHA | Paperwork | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-1160 | Uploaded
JAMNIC | L10 deck panels | 3 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.8 | 6446.0-1161 | Uploaded
JAMNIC | Column wraps @ podium | 5 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-1162 | Uploaded
CAMPHI | Sheet metal roof @ L14 canopy | 3 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.2 | 6446.0-1163 | Uploaded
CAMPHI | Wall panels @ entry vestibule | 5 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-1164 | Uploaded
STEJAC | Penthouse gutters and DS | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-1165 | Uploaded
JACJOH | Sheet metal roof @ L14 canopy (roof build up) | 3 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.8 | 6446.0-1166 | Uploaded
JACJOH | Exterior window installation | 5 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-1167 | Uploaded
GRETAR | Facade metal panel installation | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-1168 | Uploaded
CAVJAM | Basement waterproofing | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.3 | 6446.0-1169 | Uploaded
LUCLAW | Elevator shaft framing | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-1170 | Uploaded
HANTYL | Site drainage installation | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.9 | 6446.0-1171 | Uploaded
CUSCAR | Concrete foundation pouring | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-1172 | Uploaded
SLOKYL | HVAC ductwork installation | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-1173 | Uploaded
CATMAT | Interior wall framing | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-1174 | Uploaded
BAUTHA | Electrical conduit installation | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-1175 | Uploaded
JAMNIC | Fire sprinkler system installation | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-1176 | Uploaded
CAMPHI | Roof membrane installation | 3 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-1177 | Uploaded
CAMPHI | Floor tile installation | 5 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-1178 | Uploaded
STEJAC | Drywall installation | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-1179 | Uploaded
JACJOH | Parking lot asphalt paving | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-1180 | Uploaded
GRETAR | Landscape irrigation installation | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-1181 | Uploaded
CAVJAM | Structural steel erection | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.5 | 6446.0-1182 | Uploaded
JOHSCO | Guardrail installation | 6 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-1183 | Uploaded
LUCLAW | Exterior painting | 2 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.8 | 6446.0-1184 | Uploaded
LUCLAW | Interior door installation | 6 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-1185 | Uploaded
HANTYL | Window caulking and sealing | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-1186 | Uploaded
CUSCAR | Ceiling grid installation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-1187 | Uploaded
SLOKYL | Building insulation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-1188 | Uploaded
CATMAT | Hardwood flooring installation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.3 | 6446.0-1189 | Uploaded
BAUTHA | Crown molding installation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.8 | 6446.0-1190 | Uploaded
JAMNIC | Kitchen cabinetry installation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-1191 | Uploaded
CAMPHI | Bathroom fixture installation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.5 | 6446.0-1192 | Uploaded
STEJAC | Tool organization | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-1193 | Uploaded
JACJOH | Team safety meeting | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-1194 | Uploaded
GRETAR | Material delivery coordination | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-1195 | Uploaded
CAVJAM | Quality control inspection | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-1196 | Uploaded
JOHSCO | Stair railing installation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-1197 | Uploaded
LUCLAW | Building permit processing | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-1198 | Uploaded
HANTYL | Demolition work | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-1199 | Uploaded
CUSCAR | Scaffolding assembly | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-1200 | Uploaded
SLOKYL | Masonry wall construction | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-1201 | Uploaded
JOHBRI | Plumbing rough-in | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-1202 | Uploaded
CATMAT | Exterior lighting installation | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-1203 | Uploaded
BAUTHA | Rooftop HVAC unit installation | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-1204 | Uploaded
JAMNIC | Subcontractor coordination | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.2 | 6446.0-1205 | Uploaded
CAMPHI | Curtain wall installation | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-1206 | Uploaded
STEJAC | Balcony waterproofing | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-1207 | Uploaded
JACJOH | Emergency exit signage installation | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.8 | 6446.0-1208 | Uploaded
GRETAR | Project planning and scheduling | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-1209 | Uploaded
CAVJAM | Security system wiring | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.1 | 6446.0-1210 | Uploaded
JOHSCO | Penthouse siding and coping | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-1211 | Uploaded
LUCLAW | Roof screen wall | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-1212 | Uploaded
CUSCAR | Commute to Site | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-1213 | Uploaded
SLOKYL | Garage Gutters | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.8 | 6446.0-1214 | Uploaded
JOHBRI | Paperwork | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1 | 6446.0-1215 | Uploaded
CATMAT | L10 deck panels | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-1216 | Uploaded
BAUTHA | Column wraps @ podium | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-1217 | Uploaded
JAMNIC | Sheet metal roof @ L14 canopy | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-1218 | Uploaded
CAMPHI | Wall panels @ entry vestibule | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.7 | 6446.0-1219 | Uploaded
STEJAC | Penthouse gutters and DS | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-1220 | Uploaded
JACJOH | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-1221 | Uploaded
GRETAR | Exterior window installation | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-1222 | Uploaded
CAVJAM | Facade metal panel installation | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-1223 | Uploaded
JOHSCO | Basement waterproofing | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.1 | 6446.0-1224 | Uploaded
UTLJOH | Elevator shaft framing |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-1225 | Uploaded
COUMAR | Site drainage installation |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.6 | 6446.0-1226 | Uploaded
JOHBRI | Concrete foundation pouring |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-1227 | Uploaded
CATMAT | HVAC ductwork installation |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-1228 | Uploaded
BROAUS | Interior wall framing |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-1229 | Uploaded
JACJOH | Electrical conduit installation |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-1230 | Uploaded
CAVJAM | Fire sprinkler system installation |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-1231 | Uploaded
JOHSCO | Roof membrane installation |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-1232 | Uploaded
BLARYA | Floor tile installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-1233 | Uploaded
QUINJR | Drywall installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-1234 | Uploaded
JOHBRI | Parking lot asphalt paving | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-1235 | Uploaded
QUITIT | Landscape irrigation installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-1236 | Uploaded
CATMAT | Structural steel erection | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-1237 | Uploaded
BROAUS | Guardrail installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-1238 | Uploaded
BAUTHA | Exterior painting | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-1239 | Uploaded
WISJER | Interior door installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-1240 | Uploaded
STEJAC | Window caulking and sealing | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-1241 | Uploaded
JACJOH | Ceiling grid installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-1242 | Uploaded
GRETAR | Building insulation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.6 | 6446.0-1243 | Uploaded
CAVJAM | Hardwood flooring installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-1244 | Uploaded
JOHSCO | Crown molding installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-1245 | Uploaded
BLARYA | Kitchen cabinetry installation | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1 | 6446.0-1246 | Uploaded
QUINJR | Bathroom fixture installation | 5 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-1247 | Uploaded
JOHBRI | Tool organization | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-1248 | Uploaded
OTTJOH | Team safety meeting | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-1249 | Uploaded
QUITIT | Material delivery coordination | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-1250 | Uploaded
CATMAT | Quality control inspection | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-1251 | Uploaded
BROAUS | Stair railing installation | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-1252 | Uploaded
BAUTHA | Building permit processing | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-1253 | Uploaded
CAMPHI | Demolition work | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-1254 | Uploaded
WISJER | Scaffolding assembly | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-1255 | Uploaded
STEJAC | Masonry wall construction | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-1256 | Uploaded
JACJOH | Plumbing rough-in | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-1257 | Uploaded
GRETAR | Exterior lighting installation | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-1258 | Uploaded
CAVJAM | Rooftop HVAC unit installation | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-1259 | Uploaded
JOHSCO | Subcontractor coordination | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-1260 | Uploaded
QUINJR | Curtain wall installation | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-1261 | Uploaded
JOHBRI | Balcony waterproofing | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-1262 | Uploaded
QUITIT | Emergency exit signage installation | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-1263 | Uploaded
CATMAT | Project planning and scheduling | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.3 | 6446.0-1264 | Uploaded
BROAUS | Security system wiring | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-1265 | Uploaded
BAUTHA | Penthouse siding and coping | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.7 | 6446.0-1266 | Uploaded
JAMNIC | Roof screen wall | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-1267 | Uploaded
CAMPHI | Commute to Site | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-1268 | Uploaded
WISJER | Garage Gutters | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-1269 | Uploaded
STEJAC | Paperwork | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-1270 | Uploaded
JACJOH | L10 deck panels | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-1271 | Uploaded
GRETAR | Column wraps @ podium | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-1272 | Uploaded
CAVJAM | Sheet metal roof @ L14 canopy | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-1273 | Uploaded
JOHSCO | Wall panels @ entry vestibule | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-1274 | Uploaded
QUINJR | Penthouse gutters and DS | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-1275 | Uploaded
JOHBRI | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-1276 | Uploaded
OTTJOH | Exterior window installation | 6 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.1 | 6446.0-1277 | Uploaded
QUITIT | Facade metal panel installation | 1 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-1278 | Uploaded
QUITIT | Basement waterproofing | 7 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-1279 | Uploaded
CATMAT | Elevator shaft framing | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.6 | 6446.0-1280 | Uploaded
BROAUS | Site drainage installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6 | 6446.0-1281 | Uploaded
BAUTHA | Concrete foundation pouring | 5 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-1282 | Uploaded
JAMNIC | HVAC ductwork installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.8 | 6446.0-1283 | Uploaded
CAMPHI | Interior wall framing | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-1284 | Uploaded
WISJER | Electrical conduit installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.9 | 6446.0-1285 | Uploaded
STEJAC | Fire sprinkler system installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-1286 | Uploaded
JACJOH | Roof membrane installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1 | 6446.0-1287 | Uploaded
GRETAR | Floor tile installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.9 | 6446.0-1288 | Uploaded
CAVJAM | Drywall installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-1289 | Uploaded
JOHSCO | Parking lot asphalt paving | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-1290 | Uploaded
QUINJR | Landscape irrigation installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6 | 6446.0-1291 | Uploaded
JOHBRI | Structural steel erection | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-1292 | Uploaded
OTTJOH | Guardrail installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-1293 | Uploaded
QUITIT | Exterior painting | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-1294 | Uploaded
CATMAT | Interior door installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.2 | 6446.0-1295 | Uploaded
BROAUS | Window caulking and sealing | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.9 | 6446.0-1296 | Uploaded
BAUTHA | Ceiling grid installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-1297 | Uploaded
JAMNIC | Building insulation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-1298 | Uploaded
CAMPHI | Hardwood flooring installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-1299 | Uploaded
WISJER | Crown molding installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.2 | 6446.0-1300 | Uploaded
STEJAC | Kitchen cabinetry installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-1301 | Uploaded
JACJOH | Bathroom fixture installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.2 | 6446.0-1302 | Uploaded
GRETAR | Tool organization | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-1303 | Uploaded
CAVJAM | Team safety meeting | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-1304 | Uploaded
JOHSCO | Material delivery coordination | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.9 | 6446.0-1305 | Uploaded
BROAUS | Quality control inspection |  | 6 | 2024-04-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-1306 | Uploaded
JOHBRI | Stair railing installation |  | 6 | 2024-04-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-1307 | Uploaded
CATMAT | Building permit processing |  | 6 | 2024-04-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.9 | 6446.0-1308 | Uploaded
GRETAR | Demolition work |  | 6 | 2024-04-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-1309 | Uploaded
CAVJAM | Scaffolding assembly |  | 6 | 2024-04-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-1310 | Uploaded
BROAUS | Masonry wall construction | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-1311 | Uploaded
JOHBRI | Plumbing rough-in | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.4 | 6446.0-1312 | Uploaded
OTTJOH | Exterior lighting installation | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.4 | 6446.0-1313 | Uploaded
QUITIT | Rooftop HVAC unit installation | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-1314 | Uploaded
CATMAT | Subcontractor coordination | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.9 | 6446.0-1315 | Uploaded
JAMNIC | Curtain wall installation | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-1316 | Uploaded
CAMPHI | Balcony waterproofing | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-1317 | Uploaded
WISJER | Emergency exit signage installation | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.7 | 6446.0-1318 | Uploaded
STEJAC | Project planning and scheduling | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-1319 | Uploaded
JACJOH | Security system wiring | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-1320 | Uploaded
GRETAR | Penthouse siding and coping | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-1321 | Uploaded
CAVJAM | Roof screen wall | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.4 | 6446.0-1322 | Uploaded
BROAUS | Commute to Site | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-1323 | Uploaded
BAUTHA | Garage Gutters | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.3 | 6446.0-1324 | Uploaded
JOHBRI | Paperwork | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-1325 | Uploaded
OTTJOH | L10 deck panels | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-1326 | Uploaded
QUITIT | Column wraps @ podium | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-1327 | Uploaded
CATMAT | Sheet metal roof @ L14 canopy | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.5 | 6446.0-1328 | Uploaded
JAMNIC | Wall panels @ entry vestibule | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-1329 | Uploaded
CAMPHI | Penthouse gutters and DS | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.8 | 6446.0-1330 | Uploaded
WISJER | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-1331 | Uploaded
GRETAR | Exterior window installation | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-1332 | Uploaded
CAVJAM | Facade metal panel installation | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-1333 | Uploaded
BROAUS | Basement waterproofing | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-1334 | Uploaded
BAUTHA | Elevator shaft framing | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.8 | 6446.0-1335 | Uploaded
JOHBRI | Site drainage installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-1336 | Uploaded
OTTJOH | Concrete foundation pouring | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-1337 | Uploaded
CATMAT | HVAC ductwork installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-1338 | Uploaded
JAMNIC | Interior wall framing | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8 | 6446.0-1339 | Uploaded
CAMPHI | Electrical conduit installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6 | 6446.0-1340 | Uploaded
WISJER | Fire sprinkler system installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2 | 6446.0-1341 | Uploaded
STEJAC | Roof membrane installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-1342 | Uploaded
JACJOH | Floor tile installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.3 | 6446.0-1343 | Uploaded
GRETAR | Drywall installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-1344 | Uploaded
CAVJAM | Parking lot asphalt paving | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-1345 | Uploaded
BROAUS | Landscape irrigation installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.9 | 6446.0-1346 | Uploaded
BAUTHA | Structural steel erection | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.1 | 6446.0-1347 | Uploaded
JOHBRI | Guardrail installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-1348 | Uploaded
OTTJOH | Exterior painting | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.4 | 6446.0-1349 | Uploaded
QUITIT | Interior door installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-1350 | Uploaded
CATMAT | Window caulking and sealing | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-1351 | Uploaded
JAMNIC | Ceiling grid installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-1352 | Uploaded
CAMPHI | Building insulation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-1353 | Uploaded
WISJER | Hardwood flooring installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.8 | 6446.0-1354 | Uploaded
STEJAC | Crown molding installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-1355 | Uploaded
JACJOH | Kitchen cabinetry installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.1 | 6446.0-1356 | Uploaded
GRETAR | Bathroom fixture installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.6 | 6446.0-1357 | Uploaded
CAVJAM | Tool organization | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.2 | 6446.0-1358 | Uploaded
BROAUS | Team safety meeting | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-1359 | Uploaded
BAUTHA | Material delivery coordination | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.1 | 6446.0-1360 | Uploaded
JOHBRI | Quality control inspection | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-1361 | Uploaded
OTTJOH | Stair railing installation | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-1362 | Uploaded
QUITIT | Building permit processing | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.8 | 6446.0-1363 | Uploaded
CATMAT | Demolition work | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-1364 | Uploaded
JAMNIC | Scaffolding assembly | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-1365 | Uploaded
CAMPHI | Masonry wall construction | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-1366 | Uploaded
WISJER | Plumbing rough-in | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3 | 6446.0-1367 | Uploaded
STEJAC | Exterior lighting installation | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-1368 | Uploaded
JACJOH | Rooftop HVAC unit installation | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.6 | 6446.0-1369 | Uploaded
GRETAR | Subcontractor coordination | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.8 | 6446.0-1370 | Uploaded
CAVJAM | Curtain wall installation | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-1371 | Uploaded
QUINJR | Balcony waterproofing | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.5 | 6446.0-1372 | Uploaded
JOHBRI | Emergency exit signage installation | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-1373 | Uploaded
OTTJOH | Project planning and scheduling | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7 | 6446.0-1374 | Uploaded
QUITIT | Security system wiring | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.6 | 6446.0-1375 | Uploaded
CATMAT | Penthouse siding and coping | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-1376 | Uploaded
BROAUS | Roof screen wall | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-1377 | Uploaded
BAUTHA | Commute to Site | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-1378 | Uploaded
JAMNIC | Garage Gutters | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.1 | 6446.0-1379 | Uploaded
CAMPHI | Paperwork | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.2 | 6446.0-1380 | Uploaded
WISJER | L10 deck panels | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-1381 | Uploaded
STEJAC | Column wraps @ podium | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.3 | 6446.0-1382 | Uploaded
JACJOH | Sheet metal roof @ L14 canopy | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.5 | 6446.0-1383 | Uploaded
GRETAR | Wall panels @ entry vestibule | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-1384 | Uploaded
CAVJAM | Penthouse gutters and DS | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.8 | 6446.0-1385 | Uploaded
JOHSCO | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-1386 | Uploaded
QUINJR | Exterior window installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.9 | 6446.0-1387 | Uploaded
JOHBRI | Facade metal panel installation | 6.5 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-1388 | Uploaded
OTTJOH | Basement waterproofing | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-1389 | Uploaded
CATMAT | Elevator shaft framing | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4 | 6446.0-1390 | Uploaded
BROAUS | Site drainage installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.4 | 6446.0-1391 | Uploaded
BAUTHA | Concrete foundation pouring | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-1392 | Uploaded
JAMNIC | HVAC ductwork installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-1393 | Uploaded
CAMPHI | Interior wall framing | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.9 | 6446.0-1394 | Uploaded
WISJER | Electrical conduit installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6 | 6446.0-1395 | Uploaded
STEJAC | Fire sprinkler system installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-1396 | Uploaded
JACJOH | Roof membrane installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-1397 | Uploaded
GRETAR | Floor tile installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-1398 | Uploaded
CAVJAM | Drywall installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.4 | 6446.0-1399 | Uploaded
JOHSCO | Parking lot asphalt paving | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-1400 | Uploaded
HOYWES | Landscape irrigation installation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.9 | 6446.0-1401 | Uploaded
QUINJR | Structural steel erection | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-1402 | Uploaded
JOHBRI | Guardrail installation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.3 | 6446.0-1403 | Uploaded
CATMAT | Exterior painting | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.9 | 6446.0-1404 | Uploaded
BROAUS | Interior door installation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.8 | 6446.0-1405 | Uploaded
BAUTHA | Window caulking and sealing | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.5 | 6446.0-1406 | Uploaded
JAMNIC | Ceiling grid installation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-1407 | Uploaded
CAMPHI | Building insulation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-1408 | Uploaded
WISJER | Hardwood flooring installation | 1 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-1409 | Uploaded
WISJER | Crown molding installation | 7 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.9 | 6446.0-1410 | Uploaded
STEJAC | Kitchen cabinetry installation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.7 | 6446.0-1411 | Uploaded
JACJOH | Bathroom fixture installation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.6 | 6446.0-1412 | Uploaded
GRETAR | Tool organization | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.6 | 6446.0-1413 | Uploaded
CAVJAM | Team safety meeting | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.2 | 6446.0-1414 | Uploaded
JOHSCO | Material delivery coordination | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.8 | 6446.0-1415 | Uploaded
HOYWES | Quality control inspection | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.7 | 6446.0-1416 | Uploaded
OETBRO | Stair railing installation | 7.5 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.1 | 6446.0-1417 | Uploaded
QUINJR | Building permit processing | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1 | 6446.0-1418 | Uploaded
LUCLAW | Demolition work | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.5 | 6446.0-1419 | Uploaded
JOHBRI | Scaffolding assembly | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 2.7 | 6446.0-1420 | Uploaded
CATMAT | Masonry wall construction | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.4 | 6446.0-1421 | Uploaded
BROAUS | Plumbing rough-in | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.1 | 6446.0-1422 | Uploaded
BAUTHA | Exterior lighting installation | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.7 | 6446.0-1423 | Uploaded
JAMNIC | Rooftop HVAC unit installation | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-1424 | Uploaded
CAMPHI | Subcontractor coordination | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.7 | 6446.0-1425 | Uploaded
WISJER | Curtain wall installation | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-1426 | Uploaded
STEJAC | Balcony waterproofing | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-1427 | Uploaded
JACJOH | Emergency exit signage installation | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.5 | 6446.0-1428 | Uploaded
OSBKEV | Project planning and scheduling | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.7 | 6446.0-1429 | Uploaded
GRETAR | Security system wiring | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-1430 | Uploaded
CAVJAM | Penthouse siding and coping | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.6 | 6446.0-1431 | Uploaded
JOHSCO | Roof screen wall | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.3 | 6446.0-1432 | Uploaded
LUCLAW | Commute to Site | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5.4 | 6446.0-1433 | Uploaded
JOHBRI | Garage Gutters | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.6 | 6446.0-1434 | Uploaded
CATMAT | Paperwork | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 4.2 | 6446.0-1435 | Uploaded
BROAUS | L10 deck panels | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 6.2 | 6446.0-1436 | Uploaded
BAUTHA | Column wraps @ podium | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.1 | 6446.0-1437 | Uploaded
CAMPHI | Sheet metal roof @ L14 canopy | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 3.4 | 6446.0-1438 | Uploaded
WISJER | Wall panels @ entry vestibule | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 1.3 | 6446.0-1439 | Uploaded
STEJAC | Penthouse gutters and DS | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-1440 | Uploaded
JACJOH | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 8.7 | 6446.0-1441 | Uploaded
GRETAR | Exterior window installation | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 7.9 | 6446.0-1442 | Uploaded
JOHSCO | Facade metal panel installation | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone | 5 | 6446.0-1443 | Uploaded
GROJER | Basement waterproofing | 2 |  | 2024-01-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:1/22/2024 2:26:08 PM_Verified by:GROSS, JEREMY | 35 Stone | 3.7 | 6446.0-1444 | Uploaded
GROJER | Elevator shaft framing | 2 |  | 2024-01-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:1/22/2024 2:26:08 PM_Verified by:GROSS, JEREMY | 35 Stone | 4.5 | 6446.0-1445 | Uploaded
GROJER | Site drainage installation | 4 |  | 2024-01-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:1/16/2024 10:47:45 AM_Verified by:GROSS, JEREMY | 35 Stone | 7.6 | 6446.0-1446 | Uploaded
GROJER | Concrete foundation pouring | 4.5 |  | 2024-01-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:1/8/2024 7:20:32 AM_Verified by:GROSS, JEREMY | 35 Stone | 8.3 | 6446.0-1447 | Uploaded
GROJER | HVAC ductwork installation | 1 |  | 2023-12-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:12/15/2023 11:53:57 AM_Verified by:GROSS, JEREMY | 35 Stone | 5.7 | 6446.0-1448 | Uploaded
GROJER | Interior wall framing | 2 |  | 2023-12-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:12/8/2023 3:05:43 PM_Verified by:GROSS, JEREMY | 35 Stone | 4.4 | 6446.0-1449 | Uploaded
GROJER | Electrical conduit installation | 1.5 |  | 2023-12-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:12/8/2023 3:05:43 PM_Verified by:GROSS, JEREMY | 35 Stone | 6.5 | 6446.0-1450 | Uploaded
LUCLAW | Fire sprinkler system installation | 1.5 |  | 2023-10-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:10/16/2023 7:15:15 AM_Verified by:LUCAS, LAWRENCE | 35 Stone | 6.7 | 6446.0-1451 | Uploaded
LUCLAW | Roof membrane installation | 4 |  | 2023-10-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:10/16/2023 7:15:15 AM_Verified by:LUCAS, LAWRENCE | 35 Stone | 2.2 | 6446.0-1452 | Uploaded
LUCLAW | Floor tile installation | 1.5 |  | 2023-10-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:10/9/2023 6:53:46 AM_Verified by:LUCAS, LAWRENCE | 35 Stone | 6.4 | 6446.0-1453 | Uploaded
LUCLAW | Drywall installation | 4 |  | 2023-10-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:10/9/2023 6:53:46 AM_Verified by:LUCAS, LAWRENCE | 35 Stone | 5 | 6446.0-1454 | Uploaded
GROJER | Parking lot asphalt paving | 1 |  | 2023-06-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/26/2023 11:14:13 AM_Verified by:GROSS, JEREMY | 35 Stone | 1.8 | 6446.0-1455 | Uploaded
GROJER | Landscape irrigation installation | 2 |  | 2023-06-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/26/2023 11:14:13 AM_Verified by:GROSS, JEREMY | 35 Stone | 2.4 | 6446.0-1456 | Uploaded
GROJER | Structural steel erection | 1.5 |  | 2023-06-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/20/2023 7:57:08 AM_Verified by:GROSS, JEREMY | 35 Stone | 2.1 | 6446.0-1457 | Uploaded
GROJER | Guardrail installation | 1.5 |  | 2023-06-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/20/2023 7:57:08 AM_Verified by:GROSS, JEREMY | 35 Stone | 8.9 | 6446.0-1458 | Uploaded
GROJER | Exterior painting | 5 |  | 2023-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/22/2023 12:44:13 PM_Verified by:GROSS, JEREMY | 35 Stone | 3.8 | 6446.0-1459 | Uploaded
GROJER | Interior door installation | 2 |  | 2023-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/15/2023 1:41:11 PM_Verified by:GROSS, JEREMY | 35 Stone | 8 | 6446.0-1460 | Uploaded
GROJER | Window caulking and sealing | 1.5 |  | 2023-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/15/2023 1:41:11 PM_Verified by:GROSS, JEREMY | 35 Stone | 2.3 | 6446.0-1461 | Uploaded
6446.0-1462
6446.0-1463
6446.0-1464
6446.0-1465
6446.0-1466
6446.0-1467
6446.0-1468
6446.0-1469
6446.0-1470
6446.0-1471
6446.0-1472
6446.0-1473
6446.0-1474
6446.0-1475
6446.0-1476
6446.0-1477
6446.0-1478
6446.0-1479
6446.0-1480
6446.0-1481
6446.0-1482
6446.0-1483
6446.0-1484
6446.0-1485
6446.0-1486
6446.0-1487
6446.0-1488
6446.0-1489
6446.0-1490
6446.0-1491
6446.0-1492
6446.0-1493
6446.0-1494
6446.0-1495
6446.0-1496
6446.0-1497
6446.0-1498
6446.0-1499